Gansu Urban Infrastructure Construction and Wetland Protection Project

(Loan No.: 2903-china)

Resettlement Monitoring and Evaluation report

(No.8)

Prepared by Shanghai Yiji Construction Project Consulting Co. Ltd.

May 2017

Responsible Person: Zongfa Wu, Jin Gong

Report Writing: Zongfa Wu, Jin Gong, Lizhi Tang, Fang Hu, Wenyi Xia,        Yun Guo

E-mail:   gjwzf@263.net

Abbreviation

| ADB | Asian Development Bank |
| --- | --- |
| AH | Project Affected Household |
| AP | Project Affected Person |
| HH | Household |
| IA | Implementing Agency |
| Mu | Chinese measurement unit for land area（1mu =0.0667 ha） |
| PMO | ADB Financed Zhangye Project Management Office |
| PPTA | Project preparation technical assistance |
| PRO | Project Resettlement Office under ZGDFLMC |
| RP | Resettlement Plan |
| SES | Social economic survey |
| m2 | Square meters |
| ZGDFLMC | Zhangye Ganzhou District Foreign Loan Management Committee |
| Yuan | The unit of Chinese currency, CNY |

Note： all abbreviations were explained in the text, here only introduces important part.

TABLE OF CONTENTS

1.1    Zhanyge Project	1

1.2    Dingxi Project	1

2.    Overall resettlement	3

2.1    Overall situation of Zhangye City	3

2.2	Land acquisition and resettlement of Dingxi City	3

3    Progress of Resettlement	5

3.1    Progress of Zhangye City	5

3.1.1  land acquisition progress	5

3.1.2  House construction Progress	6

3.2    Progress of Dingxi City	7

4    Resettlement Policies	9

4.1	Policy of Zhangye City	9

4.2	Policy of Dingxi City	10

5    Income and Rehabilitation and Sample HHs Survey	14

5.1    Sample surveys of Zhangye City	14

5.1.1    Design of Sample Survey	14

5.1.2	Sample HH survey	14

5.1.3  Income Recover	18

5.2    Sample Survey of Dingxi City	18

5.2.1    Design of Sample Survey	18

5.2.2	Sample HH survey	18

5.2.3    Income Recover	21

6    House Relocation	22

6.1    House Relocation of Zhangye City	22

6.2    House relocation of Dingxi City	25

7   Restoration of infrastructure	31

7.1     Infrastructure of Zhangye City	31

7.2    Infrastructure of Dingxi City	31

8    Resettlement Fund	32

8.1    Resettlement Fund of Zhangye City	32

8.2    Resettlement Fund of Dingxi City	33

9    Participation and information disclosure	35

9.1    Participation and information disclosure of Zhangye City	35

9.2    Participation and information disclosure of Dingxi City	35

10    Organization and Management	39

10.1    Organization and Management of Zhangye City	39

10.2    Organization and Management of Dingxi City	39

11    Monitoring and Evaluation	40

12   Conclusions and Suggestions	41

12.1    conclusions and suggestions of Zhangye City	41

12.1.1    Conclusions	41

12.1.2    Suggestions	41

12.2    conclusions and suggestions of Dingxi City	41

12.2.1   Conclusions	41

12.2.2   Suggestions	42

Annex I   Interviews	43

1.1    Interviews of Zhangye City	43

1.2    Interviews of Dingxi City	56

Annex 2 Basic monitoring data	63

2.1    Basic monitoring data of Zhangye City	63

0. Reply and comments for Memorandum of Understanding (22-26 Aug.2016)

Zhangye

Table 0-1 Zhangye Land Acquisition and Resettlement Status and Follow-up Actions

| No | Name of the road | Affected village | Progress | Proposed Action |
| --- | --- | --- | --- | --- |
| CZ1 | Zhaowu Rd. | Nanhua，Xiguan， | The land acquisition was completed. In the east part (500 m) of the east section, house demolition with restaurants will affect 96 HHs, although the ADB road will just affect several HHs. | The PMO proposed to drop the 500 m part and ADB agreed during the mission. |
| CZ2 | Gaotai Bei Rd. | Group 9, Nanhua, | The land acquisition was completed. At the cross of West Linsong Street (CZ4), 65 houses need to be demolished. | The construction of new resettlement houses is finished. A third of the agreements have been signed, and the home demolition is planned to be completed before end of May 2017. |
| CZ3 | Alley Avenue(north 3rd Ring) | Beiguan, Liuquan, Baita | LAR and construction is completed | NA |
| CZ3 | Juyan Rd. | Beiguan, Liuguan |  |  |
| CZ4 | Linsong Xi Street (Minghai Xi Rd.) | Nanhua，Xiguan | The land acquisition was completed. 10 houses of Group 9 of Nanhua Village need to be demolished at the cross of North Gaotai Street (CZ2). | The new resettlement housing has been completed and the resettlement fees are in place. A third have signed the agreement, and it is planned to complete the house demolition by the end of May 2017. |
| CZ4 | Linsong Dong Street (Minghai Dong Rd.) | Xiguan，Nanhua | The land acquisition was completed. | House demolition was implemented in July 2016. |
| CZ5 | Sunan Bei Rd. | Nanhua | Completed | NA |
| CZ5 | Baita Street (Wulan Rd.) | Nanhua, Xiguan | LAR was completed. | The house demolition was implemented in July 2016. |
| CZ6 | Linze Nan Rd. | Qingsong，Nanchan | There are remaining 3 HHs. Judicial decision was issued in March 2016, which did not support the house demolition under current demolition arrangement. | In January 2017, the three HHS signed the house compensation agreement, and the houses are demolished. The road is under construction. |
| CZ6 | Yonggu Dong Rd. | Qingsong，Nanchan | Land acquisition is ongoing and some fruit trees of Group 5 of QIngsong Village was not acquired. | No house demolition is involved. PMO plans to complete before August 2017. Some fruit trees of Comunity 5 in Qingsong Village have not been requisitioned yet. There is no progress, since the APs have objections to the RP. |
| CZ7 | Nanhua Street (Liaoquan Rd.) | Qingsong | One pig farm and 58 houses of Group 2 of Qingsong Village need to be demolished. Land of Qingsong 6 she village has not been acquired as people ask more compensation for the trees on the land. | Among the 58 AHs of Group 2, Qingsong Village, 30 HHs have been demolished, and the other 28 HHs are under negotiation. The new houses of the AHs will be completed in June 2017, and the pig farm at end of August 2017. The land acquisition of Community 6 in Qingsong Village has been finished. |
| Z7 | Yuguan Rd.(Huota Rd.) | Qingsong，Nanhua | Completed. | NA |
| CZ9 | Wenchang Rd.(Xuefu Rd.) | Beiguan | The PMO changes the alignment of this road to avoid house demolition but 7 AHs of Group 1 and 4 AHs of Group 2 of Beiguan Village have not been moved. The house demolition of Beiguan Group 2 was delayed by unavailability of resettlement cost. LAR of Beiguan Group 1 has dispute on land compensation rates. | The house demolition of 7 HHs in Community1 of Beiguan Village has not been completed yet, since there are too many persons and too less lands. The 4 HHs of Community 2 has been finished. The land compensation dispute of Community 1 in Beiguan Village has not been resolved. The PMO plans to complete house demolition and land acquisition by December 2017. |
| CZ9 | Danma Street (Banqiao Rd.) | Beigua, Liuquan | Low-rent houses administrated by District Housing Bureau have not been demolished. Land acquisition of Group 1 of Liuquan Village was not included in the annual plan. 6 houses of Beiguan Group 5 have not been demolished. | The problem is not resolved. The PMO plans to complete house demolition and land acquisition by December 2017. |
| CZ11 | Minle Road | Qingsong, Xiguan. | Land of Qingsong Group 5 and 6 have not been acquired due to trees compensation dispute. | The land of Group 6 of Qingsong Village has been requisitioned. The PMO plans to complete house demolition and land acquisition by December 2017. |

Reply: As of April 30, 2017, Zhangye Project Office attaches great importance to land acquisition and resettlement, and they are currently working actively. Great Progress has been achieved, and all problems are expected to be resolved by the end of 2017.

2) For house compensation dispute with 3 AHs involved in Linze South Street, the mission was advised the 3 AHs will not be relocated under the current resettlement arrangement according to the final judicial decision in March 2016. Three options were proposed, such as the realignment of the roads to avoid the house demolition of 3 AHs, the continuous consultation with AHs or appealing for further court judgement. The mission also stressed the strict compliance with court decision in case that the loan disbursement will be suspended.

Reply: the three HHs have signed the house compensation agreement, the houses are demolished, and the road is under construction.

Please see table 0-1.

Table 0-1  Dispute settlement for the housing compensation of three HHs in South Linze Street

| Name | House compensation | Basic reward | resi | Residential spot price | Compensation for high structure standard | Subtotal | Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | yuan | yuan | yuan | yuan | yuan | yuan |  |
| Yuming Tian | 160000 | 30000 | 30000 | 50000 |  | 270000 | Nov 28, 2016 |
| Xingwen Liu | 160000 | 30000 | 30000 | 50000 |  | 270000 | Nov 28, 2016 |
| Jianbing Li | 160000 | 30000 | 30000 | 50000 | 50000 | 320000 | Nov 25, 2016 |

3) The income restoration remains a deep concern for APs with land loss either from Project land acquisition or urban development program. Skills training and job opportunities should be provided to affected farmers to facilitate a smooth transition from rural to urban livelihoods.

Reply: Interviews were conducted with Qingsong Village, Beiguan Village and Nanhua Village. Xin Dun town attaches great importance to the villagers’ employment training, which include welding, bricklaying, housekeeping and so on. There are 4 times trainings a year in each village, participating by more than 200 people/times. Affected households all have a stable work, with a monthly income of 2,000 yuan to 3,000 yuan. Interviews showed that the affected people have successfully completed the changes from rural to urban areas.  Thanks to the construction of the new district of Zhangye City, a lot of employment opportunities have been provided, which enables all APs to find a new job in the city. Meanwhile, during the land acquisition process, around 35 to 40 mu lands each group are reserved for development. The developer provided 8000 - 5000 m2 commercial shops for each group. For example, in Group 4 of Qingsong Village, according to 50 m2 per person, averagely 230 m2 commercial shops are allocated to each HH, which can be used for renting, with a rent of 28 - 35 yuan per m2.

11.The mission urged Zhangye PMO and the IAs to speed up the process of land acquisition and the guarantee the timely provision of resettlement cost. The external monitoring report should document various grievance raised by the affected persons and resolution progress.

Reply: Zhangye Project Office and the implementing agency have reached a consensus on accelerating the land acquisition progress. Some problems are resolved, and some are still doing the work.

Dingxi

Tabel 0-2  Dingxi Land Acquisition and Resettlement Status and Follow-up Actions

| Project Component | AHs by House Demolition (No.) | DMS and Assessment Completion | Compensation Agreement | Physical Relocation | Implementation Status |
| --- | --- | --- | --- | --- | --- |
| CD1 Beian Zhong Road | 13 | Feb. 2016 | May 2016 | April-July 2016 | 1.The house demolition of Beian Zhong Road was completed. 2. North Dingxi Road have been finished in April 2017. |
| CD1 Dingxibei Road | 8 | Dec. 2015 | April-July 2016 | July 2016 |  |
| CD3 Xihuan Road South Section | 63 | Oct. 2015 | March-May 2016 | July 2016 | One AH has not signed the relocation agreement (Cheng AN, prosecuted to the court, and is expected to be resolved in June 2017.). Among the 62 AHs who has already signed agreements, 62 AHs have demolished houses and moved into new houses. |
| CD4 Xihuan Road North Section |  |  |  |  | 5 AHs of Shehui association have not signed agreement. 206 AHs have been relocated. The problem is expected to be resolved on June 30, 2017. |
| CD5, CD6 Jiaotong Road | 211 | Feb. 2016 | August 2016 | Sept. 2016-March 2017 |  |
| CD7 Jaiotong Road Bridge | 0 | Nov. 2015 | Dec. 2015 | Jan.-Feb. 2016 | Land acquisition was completed. Construction commencement in March 2016. No house demolition was involved. |
| Total | 295 |  |  |  |  |

Reply: As of April 30, 2017, Dingxi Project Office attaches great importance to land acquisition and resettlement, and is working actively, and has achieved remarkable results. There are six residential HHs and a Shehuo association under negotiation. Among them, 3 HHS (Cheng AN, Yonghong MA and Jihong MA) have appealed to the court, 1 HH is hearing, and 1 HH is under negotiation. The Shehuo Association (housing area of 136 m2, need a land) is under negotiation. It is expected to be resolved on June 30, 2017.

6. As of the end of July, 295 households were affected by house demolition of the Project, among which 263 AHs have signed agreement and 220 AHs have been relocated. The mission noted house compensation of about 13 AHs of Jiaotong Road has not been fully paid because they have the illegal structures to be demolished in other locations even though the agreement was signed. IA agreed to pay off all compensation to the AHs based on the signed agreement before 30 September 2016 and solve the illegal structure demolishment in other places as a separate case.

Reply: Six residential HHs and a Shehuo association have not demolished not, the others are all resolved. According to interviews, they are satisfied.

8.The mission understood the road construction of CD3, CD5 and CD6 has difficulties in demolition of large amount of illegal structures and the resettlement cost was increased as well. Two approaches were suggested, including the continuous consultation with APs on compensation on illegal structures and appealing for legal resolution when compensation agreement cannot be reached. The mission was advised the one household affected by Xihuan Road failed to reach relocation agreement and judicial procedure maybe used for dispute resolution. It is expected the final court decision will be issued in the early of 2017. Anding District Construction Bureau official also mentioned that Municipal Administrative Law Enforcement Bureau sends inspectors daily all over the city who also takes note of the illegal buildings and they will secure the necessary evidences about those illegal buildings. The mission requested the compensation scheme for illegal structures should be evaluated in the external monitoring report.

Reply: One household has entered the judicial process, and the judicial settlement is undergoing. Illegal construction definition: According to the demolition notice on April 14, 2012, the compensation standard is 600 yuan / square meters, 700 yuan / square meters, and 800 yuan / square meter accordingly. Dingxi City Bureau of Law Enforcement coordinates for the definition. Evaluation reports shall be issued for the compensation of illegal constructions and verified by Dingxi Bureau of Law Enforcement. The compensation will be put directly into the housing compensation agreement of the affected people. According to the sample investigation, the illegal constructions of affected HHs Huan An, Qiang An, Yingwen An, Xinwen An, Yuan An, Xixian Jing, Zhigang An, and Bi Shu were all compensated according to the standards.

1    Foreword

## 1.1    Zhanyge Project

- The Zhangye Urban Infrastructure Development Component (the Project) of ADB Financed Gansu Urban Infrastructure Development and Wetland Protection Project including: (1) Urban Road Construction (17 new roads with 36.213 km length in total); (2) Wastewater and Storm water Pipeline Construction along Roads; (3) A Water Supply Plant (40,000 ton /day) and Pipeline Construction; (4) Road Ancillary works; and (v) Zhangye Wetland Protection subprojects. Among them, the Land acquisition and resettlement of Zhangye Wetland Protection Subproject has been already finished, and the Due Diligence report has been written and  was approved by ADB.

- The RP was prepared during the Project preparation stage. Update was made to RP during the project implementation stage, and approved by ADB.(16th, Sep. 2013)

- The Project will affect forty (40) groups of eleven (11) village committees in one (1) town of Ganzhou District of Zhangye City. In total, 2,142.9 mu of land will be acquired permanently, while 60 mu of land will be occupied temporarily. Among the permanently acquired land, 1,881.7 mu is cultivated land, 148.8 mu is housing site land and 79.36 mu is institutional or unit land. 3,674 persons from 1,014 HHs in total will be directly affected due to land acquisition. The area of residential housing to be demolished is 139,739 m2, affecting 1,186 persons from 310 HHs. 23 business/operating units with 9,680 m2 house will also be demolished. Since the remaining land will be adjusted and reassigned to all villagers after the land acquisition, all the 2,388 HHs from 40 groups will be in fact affected by the land acquisition.

## 1.2    Dingxi Project

- The Dingxi Urban Infrastructure Development Component (the Project) of ADB Financed Project consists of four components, including: (1) Urban Road Construction and Improvement (6 new roads and 1 improved); (2) Bridge Construction; (3) Storm water and Sewage Works; (4) Road Ancillary works such as lighting and landscape. The last three components will be constructed within the existing rights-of way of the roads, so they do not refer to any land acquisition and resettlement. These seven contract packages are planned to be divided into three batches for bidding. The first batch includes two contract packages, namely: Jiaotong Road Bridge, Xincheng Avenue Bridge and Xincheng Avenue contract packages. The second batch is theXihuan Road(North Zhengfu Road - Chengbei No.1 Road) Contract Package, and the third is Jiaotong Road(Nanba Road - Xianghegou Bridge) contract package, and Jiaotong Road(Xianghegou Bridge – North Zhengfu Road) contract package. Among them, the RP update of the first contract package has been approved by ADB on 9th October, 2013. The updated RP for the second contract package is approved by ADB on August 2014, whereas the RP for the land acquisition and house demolition of the third contract package has been completed and approved by ADB in August 2016.

# 2.    Overall resettlement

## 2.1    Overall situation of Zhangye City

- The management system for land acquisition and resettlement is: ZGDFLMC office  raised the fund for land acquisition and relocation of the project, and established land acquisition and resettlement department, which is responsible for coordinating the land acquisition and resettlement work involved in the process of construction. Ganzhou Land and Resources Bureau and Xindun Town (Changan Township) Government established Coordination Office for ADB loan projects, with overall responsibility for the project land acquisition and resettlement implementation.

- As of April 30, 2017, the project has completed land acquisition 1,713.42 mu, and a total number of 2,202 land loss HHs have received compensation. The project has completed 185 HHs’ house demolition, with 91,513 m2. 185 HHs have moved into new apartments.

- The current main problem: The acquisition negotiation for the pig farms and a small piece of woods in Qingsong Village is not completed. There are some broken rodads, affecting the effectiveness of the project.. For details, please see replies to the memorandum.

## 2.2	Land acquisition and resettlement of Dingxi City

- There are seven contract packages in Dingxi Project (divided into three batches), among which, the RP updates for contract packages No.1, No.2, No.3, No.4, and No.7(the first and second batches contract packages) have been finished and approved by ADB. The RP update for contract packages No.5 and No. 6(the third batch) is completed and is approved in August 2016.

- Land acquisition of the first batch contract packages is all completed, and the land compensation fee is already paid out.

- Anding District Bureau of Land Resources is responsible for land acquisition work.

- Dingxi City Anding District Urban Construction Bureau is responsible for house demolition, and Anding District Fangyuan Assessment Company carries out physical quantity surveys for house demolition.

- Dingxi Municipal People's Government attaches great importance to the project, and a special meeting was held. The land acquisition and house demolition has achieved great progress. The land acquisition has been completed. Attentions were given to the training of farmers, so that they have a stable job and stable income. 289 HHs have signed the agreements. There are six residential HHs and a Shehuo association under negotiation. Among them, 3 HHS (Cheng AN, Yonghong MA and Jihong MA) have appealed to the court, 1 HH is hearing, and 1 HH is under negotiation. The Shehuo Association (housing area of 136 m2, need a land) is under negotiation. It is expected to be resolved on June 30, 2017. The RP is implemented.

# 3    Progress of Resettlement

## 3.1    Progress of Zhangye City

### 3.1.1  land acquisition progress

- As of  April 30, 2017,  a total area of 1713.42 mu land acquisition completed for this project, among which 1,506.51 mu is arable land, homestead 95.52 mu, 78.66 mu is unit using land, and 33.09 mu is state-owned land, completing 78.58% of the planned land acquisition. Land acquisition is summarized in Table 3-1. For details, please see annex Table 2.1.1. A total number of 2202 HHs (7535 persons) have completed land acquisition for this project, which is 85% of the planned affected HHs. HHs affected by land acquisition are summarized in Table 3-2. For the detail of AHs, please see annex Table 2.1.2.

- Table 3-1  Land acquisition of Zhangye City

- (As of April 30, 2017) unit: mu

| Planned |  |  |  |  |  | Actual |  |  |  |  |  | Actual completed pentage |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| State owned land | Collective land |  |  |  |  | State owned land | Collective land |  |  |  |  |  |
| Forest | Arable land | House site | Unit | Subtotal | Total | Forest | Arable land | House site | Unit | Subtotal | Total | % |
| 33.09 | 1,919.26 | 148.8 | 79.36 | 2,147.42 | 2,180.51 | 33.09 | 1506.15 | 95.52 | 78.66 | 1680.33 | 1713.42 | 78.58% |

- Note: there are changes for the planned numbers after the 2015 "Due Diligence and Update Report of Zhangye South Linze Road and Wenchang Road ".

- Table 3-2  AHs by land acquisition of Zhangye Project

- (As of April 30, 2017)

| Planned |  |  |  | Actual completed |  |  |  | Actual completed percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of HHs | Population | Current arable land | Land acquisition | Number of HHs | Population | Current arable land | Land acquisition | Arable land acquisition | HH affected |
| HH | Person | Mu | Mu | HH | Person | Mu | Mu | % | % |
| 2,593 | 9,072 | 12,299 | 1,919.20 | 2,202 | 7,535 | 10,537.28 | 1,561.22 | 81% | 85% |

- Note: there are changes for the planned numbers after the 2015 "Due Diligence and Update Report of Zhangye South Linze Road and Wenchang Road ".

### 3.1.2  House construction Progress

- As of April 30, 2017, there are 185 HHs completed demolition, among which, 185 HHs have already moved into new apartments. The progress of house relocation is shown in table 3-3. For the detail of house demolition and construction progress of each village, please see annex table 2.1.3.

- As of April 30, 2017, eight (8) business operating HHs have completed demolition, with a total house area of 273 m2. The house demolition of business operating HHs is shown in table 3-4. For the detail of house demolition progress of business operating HHs, please see annex table 2.1.4.

- Table 3-3  House relocation progress of Zhangye residents

- (As of April 30, 2017) unit: m2, HH

| Planned |  |  | Actual |  |  | Actual completed percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Number of HHs | Population | Area | Number of HHs | Population | Area | Affected HH | Demolition Area |
| HH | Person | m2 | HH | Person | m2 | % | % |
| 312 | 1,194 | 140,339 | 185 | 718 | 91,513 | 59% | 65% |

- Note: there are changes for the planned numbers after the 2015 "Due Diligence and Update Report of Zhangye South Linze Road and Wenchang Road ".

- Table 3-4  House relocation progress of Zhangye business operating HHs

- (As of April 30, 2017) unit: m2, HH

| Planned |  |  | Actual |  |  | Actual completed percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Number of HHs | Worker | House | Number of HHs | Worker | House | Affected HH | Demolition Area |
| HH | Person | m2 | HH | Person | m2 | % | % |
| 23 | 68 | 9,680 | 8 | 8 | 273 | 34.78% | 2.82% |

## 3.2    Progress of Dingxi City

- As of April 30, 2017, the subprojects of the first and second batches contract packages(CD1, CD2, CD3, CD4, CD5 and CD6 ) have completed a total amount of 848.5 mu land acquisition, which is 100%of the planned, and 429 HHs(1,828  persons)are affected. The policies of the RP have been implemented in the project.

- This project (CD1，CD2，CD4) needs to demolish a total amount of 107,802 m2 house. As of April 30, 2017, 158,924m2 houses were demolished in total.

- Since the chief officers attached great importance to this project, there are 6 HHs have not completed the land acquisition and house demolition in Dingxi City.

- For the summary of land acquisition, please see table 3-5. For the summary of land acquisition affected HHs, please see table 3-6. For the progress of house demolition, please see table 3-7.

Table 3-5 summary of land acquisition (As of April 30, 2017)

| Planned |  |  |  |  |  |  | Actual |  |  |  |  |  |  | Percentage |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| State owned land | Rural land |  |  |  |  | State owned land |  | Rural land |  |  |  |  |  |  |
|  | Farmland | homestead | unit | Subtotal | Total |  |  | Farmland | homestead | unit | Subtotal | Total |  |  |
| Mu | Mu | Mu | Mu | Mu | Mu | Mu |  | Mu | Mu | Mu | Mu | Mu |  |  |
| 0 | 848.52 | 0 | 0 | 848.52 | 848.52 | 0 |  | 848.52 | 0 | 0 | 848.52 | 848.52 | 100% |  |

Table 3-6 summary of affected HHs from land acquisition (As of April 30, 2017)

| Planned |  |  |  | Actual |  |  |  | Percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| number of HHs | number of persons | current farmland | acquisitioned farmland | number of HHs | number of persons | current farmland | acquisitioned farmland |  |  |
| HHs | person | mu | mu | HHs | person | mu | mu | farmland | HHs |
| 429 | 1828 | 1142.44 | 438.83 | 429 | 1828 | 1142.44 | 438.86 | 100.01% | 100.00% |

Table 3-7 progress of house demolition (As of April 30, 2017

| Planned |  |  | Actual |  |  | Percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| number of HHs | number of persons | area | number of HHs | number of persons | area | number of HHs | area |
| HHs | person | m2 | HHs | person | m2 | % | % |
| 198 | 809 | 107,802 | 289 | 1,231 | 158,924 | 146% | 147.4% |

# 4    Resettlement Policies

## 4.1	Policy of Zhangye City

- The compensation standards for land acquisition of this project are executed on the consolidated Area price, and the road using land for each group is 45 mu, with a compensation standard of 21000-22000 yuan/mu, for those over 45 mu, the compensation standard is 60000-78000 yuan/mu. (The government regulated price for road usage land is relative low. Zhangye Municipal Government has determined that 45 mu land of each villager group will be road use land, and the excess part will be executed according to non-road use standard. The actual road use of each group is more than 45 mu.) Housing compensation standard has implemented the standards of Zhangye Municipal Government, and Xindun Town government increased the compensation standard by 16.66% to 20% in the house demolition agreements with each village. The Implementation standard is higher than that of the original ADB approved. Land compensation standards are shown in Table 4-1, and house compensation standards are shown in Table 4-2. For detailed housing compensation standards, please see annex Table 2.1.5 and Table 2.1.6.

- Table 4-1  land compensation standards

|  | Planned |  |  | Actual |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 45 mu road using land for each group |  | Over 45 mu |  |  |
| Category | Yuan/m2 | Yuan/mu | Receiving object | Yuan/m2 | Yuan/mu | Receiving object | Yuan/mu | Receiving object |
| Arable land | 31.48-32.98 | 21000-22000 | Contracting HH | 31.48-32.98 | 21000-22000 | 89.95-116.94 | 60000-78000 | Contracting HH |
| Young crops | 2.10 | 1399 | Contracting HH | 2.1 | 1399 | 2.1 | 1399 | Contracting HH |

- Table 4-2 House compensation standards

- Unit: yuan

| Project | Unit | Planned | Actual |
| --- | --- | --- | --- |
| Brick-concrete building | m2 | 800 | 928 |
| Brick-concrete Bungalow | m2 | 500 | 580 |
| Brick -wood | m2 | 350 | 406 |

## 4.2	Policy of Dingxi City

4.2.1 Land compensation standard

- Land acquisition standard of Dingxi City is 48,024 yuan/mu, while young crops standard is 2,001 yuan/mu. For land acquisition standard of Dingxi City, please see table 4-3. For house acquisition standard of Dingxi City, please see table 4-4.

- Table 4-3 Land acquisition standard of Dingxi City

| Category | Yuan / m2 | Yuan / mu | Receiving object |
| --- | --- | --- | --- |
| Arable land | 72 | 48,024 | Contracting HH |
| Young crops | 3 | 2,001 | Contracting HH |
| Total | 75 | 50,025 | Contracting HH |

- Table 4-4 House acquisition standard of Dingxi City

|  |  |  | Planned | Actual | Remark |
| --- | --- | --- | --- | --- | --- |
| Monetary compensation | house | yuan/m2 | evaluation | 1678 |  |
|  | transfer | yuan/HH annual | 2400 | 2400 |  |
| Property swap | house | yuan/ m2 | Property swap | Property swap | New apartment price |
|  | arrange transfer by themselves | yuan/HH monthly | 600 | 600 |  |
|  | subsidy for house purchase | yuan | 84000 |  |  |
| Relocation | house | yuan/m2 | evaluation | 1678 |  |
|  | homestead | m2 | 196 | 196 |  |
|  | transfer | yuan/HH annual | 2400 | 2400 |  |

4.2.2 Dingxi compensation plan for house demolition

- (1) Compensation method

- The house demolition is carried out in three ways: monetary compensation, property rights exchange, and remote relocation and the compensation is made according to evaluation results from the qualified real estate professional agency. For non-residential buildings, a one-time monetary compensation is paid based on the assessment results, and for the area around the house of the affected HHs, the compensation is 90 yuan per m2.

- Subsidies for the business-stop of Enterprises and self-employed households within the acquisition scope will be determined by the tax certificate provided by the APs. The compensation for commercial and service industries are based on six months, whereas the industrial production sector is one year. For those who cannot provide proof of tax certificates, the compensation will be made according to the actual operational construction area, which is 30 yuan per m2 per month. The compensation for commercial and service industries is based on six months, whereas the industrial production sector is one year. After the signature of compensation agreement for housing demolition, the APs must empty and handover the acquisitioned houses within the relocation period stated in the compensation agreement. A relocation subsidy of 2400 yuan shall be paid to each affected HH, while 20 yuan per m2 shall be paid to enterprises according to the construction area.

- （2）Cash Compensation

- Combined with the market price of the same location, same period and similar real estate, the amount of monetary compensation shall be determined by the consultation between housing acquisition department and APs. If homesteads of farmers are involved, the compensation shall be made in accordance with land acquisition price. After the signing of the housing acquisition agreement, 40% of the total compensation amount shall be paid to APs by the acquirer within 10 days. The APs shall empty and handover the acquisitioned houses, and after verification and acceptance of the acquirer, the rest of the compensation shall be paid within 10 days.

- （3））Property swap

- Property swap is implemented according to the proportion of housing construction area, among which the unit apartment buildings are exchanged 1:1 according to inside construction area, and other houses are exchanged according to "Housing equity swap ratio conversion table". The housing construction area is calculated according to the actual housing construction area of the APs before the notice of housing acquisition.

- Property swap is carried out in accordance with the principle of  "Equivalent exchange, complementarity spread, and the one who first sign a contract can choose the apartment first". The APs shall choose the property swap houses among the resettlement houses determined by the acquirer.

- The housing construction area for property swap choose by the APs should be in accordance with the construction area of the acquisitioned houses, and shall not exceed 300 m2. If the actual swap area is smaller than the original exchange area, the difference shall be compensated in the way of one-time monetary compensation according to the evaluation. If the actual swap area is bigger than the original exchange area, the difference shall be settled according to the market price of the same period, same location and similar real estate. If the actual exchange area of APs is bigger than 300 m2 due to their own housing needs, and they are willing to pay the purchase price with the remaining compensation, they may enjoy the cost price of the resettlement housing, till the remaining compensation is used up.

- For residential houses with property right swap, during the transitional period, the acquirer shall pay temporary relocation (rent subsidy) to the APs, which is 600 yuan per HH per month and 50 yuan per person per month. The subsidy period starts from the date when the APs empty and handover the houses, within the verification and acceptance of the acquirer, and till the date of the handover of swap houses.

- The decoration and attachments of the acquisitioned houses are not for property swap, and shall be paid in the way of monetary compensation according to assessment.

- （4）Remote Relocation

- For the APs who choose remote relocation, the following requirements need to be met:

- (i). Possess permanent agriculture accounts within the township (for people within the urban planning area, subjects to related certificates). (ii). Must be the APs, who have no other homesteads in this city after house demolition.

- Remote relocation should be conducted by allocating homestead to APs for resettlement. The APs shall build the houses themselves according to the unified plan of the acquirer. The payment method of demolition compensation is the same as monetary compensation, but 20% house construction guarantee must be reserved, and shall be paid all one-time after the APs build the houses in accordance with the unified plan of the acquirer and verified and qualified by the acquirer.

- Only one homestead will be allocated to each HH for relocation, and the area is 196 m2. If the area acquired is less than 196 m2, then the allocated area should be 196 m2, and the difference in land area will not be compensated. If the area acquired is more than 196 m2, the exceeding area will be compensated according to the local land acquisition price. If additional homestead is really needed for the APs due to household separation, under the premise of meeting the relocation choices, after examination and verification by the acquirer according to the above conditions, the homestead can be allocated after payment of 100,000 yuan infrastructure fee from the APs .

- Remote relocation should be carried out in accordance with the principle of “who signs the contract first, who can select the homestead first”, and unified allocate by the acquirer according to the order.

- For APs who choose remote relocation, the homestead shall be allocated by the acquirer within 10 days after the demolition of acquisitioned houses and attachments. If the acquirer does not allocate a homestead to the AP within 10 days, a temporary resettlement subsidy (renting subsidy) shall be paid till the allocation of the homestead according to the property swap method.

# 5    Income and Rehabilitation and Sample HHs Survey

## 5.1    Sample surveys of Zhangye City

### 5.1.1    Design of Sample Survey

- There are 50 baseline sample survey HHs, and they are shown in table 5-1:

Table 5-1    Baseline sample survey HHs

| Township | Village | HH |
| --- | --- | --- |
| Xindun | Beiguan | 15 |
|  | Qingsong | 15 |
|  | Nanhua | 20 |
|  | Total | 50 |

### 5.1.2	Sample HH survey

- Sample HHs are located three villages of one town, with an average population of 4.28 people and income per capita of 160,75yuan. The arable land per capita before the land acquisition is 1.43 mu. Wage accounts for 10% of total income of sample HHs, while family operating income accounts for 86%, and property income and transfer income account for 1% and 2% respectively. Income composition of sample HHs is shown in table 5-2. Among the expenditure of sample HHs, operating expenses account for 51%, while living expenses account for 43%. Sample HHs expenditure composition is shown in Table 5-3, and survey results of per capita income of sample HHs are shown in Table 5-4, for details, please see Annex 2.1.7. Among the surveyed 50 sample HHs in October 2015, there are 60 TV sets, 46 refrigerators, 56 washing machines, 64 motorcycles, one large livestock, 51 network units, 128 telephones, 33 cars, and there are no tractors and pumps. Family property of sample HHs is shown in Table 5-5. For details of family property of sample HHs, please see annex 2.1.8.

- Tracking and Survey of Sample HHs is conducted during the second monitoring and evaluation each year. The income composition of sample HHs are comprehensive identified by village level investigation information and sample HHs survey. During the sample HHs survey, in order to facilitate the investigation, the income of self-contracted land is defined as agriculture income, and the others are defined as wage income. The above investigation method is very different from the statistical caliber of primary industry, secondary industry and tertiary industries. The decline in the income of sample households in 2015 compared to 2014 was mainly because several households had a very good business in 2014, but poor business in 2015. There was still a small increase for most people's income.

- Table 5-2  Income composition of Sample HHs of Zhangye City (Baseline survey)

| Category | Industry | Percentage |
| --- | --- | --- |
| Wage income |  | 10% |
| Family operating income |  | 86% |
|  | Primary industry | 73% |
|  | Secondary industry | 2% |
|  | Tertiary industry | 11% |
| Property income |  | 1% |
| Transfer income |  | 2% |
| Total income |  | 100% |

- Table 5-3  Expenditure composition of sample HHs of Zhangye City (Baseline survey)

| Operation expenses |  | 51% |
| --- | --- | --- |
| Purchase expenditure of fixed assets |  | 1% |
| Tax expenses |  | 0% |
| Living expenses |  | 43% |
| Property expenses |  | 0% |
| Transfer Expenditure |  | 4% |

- Table 5-4  Income and resource situation of sample HHs of Zhangye City (per capital) (as of 31st October 2016 )

| Town | Village | HH | population | Income |  |  | Before land acquisition |  |  |  | Land acquisition |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Agriculture | Working outside | Subtotal | Arable land | Dry land | Garden | Subtotal | Arable land | Dry land | Garden | Subtotal | Compensation fee |
|  |  |  |  | Yuan | Yuan | Yuan | Mu | Mu | Mu | Mu | Mu | Mu | Mu | Mu | Yuan |
| Xindun | Beiguan | 15 | 78 | 0 | 24744 | 24744 | 0.86 | 0 | 0 | 0.86 | 0.86 | 0 | 0 | 0.86 | 142000 |
|  | Qingsong | 15 | 59 | 0 | 9951 | 9951 | 1.40 | 0 | 0 | 1.40 | 1.40 | 0 | 0 | 1.40 | 154237 |
|  | Nanhua | 20 | 77 | 0 | 11987 | 11987 | 2.03 | 0 | 0 | 2.03 | 2.03 | 0 | 0 | 2.03 | 53312 |
| Per capital |  | 50 | 214 | 0 | 16075 | 16075 | 1.43 | 0 | 0 | 1.43 | 1.43 | 0 | 0 | 1.43 | 349549 |

- Table 5-5  Family property situation of sample HHs of Zhangye City (as of 31st October 2016)

| Town | village | HH | Room | House area | TV | Refrigerator | Washing machine | Tractor | Motorcycle | Pump | Big living stock | Internet | Telephone | Car |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Unit | M2 | Set | Set | Set | Set | Set | Set |  |  |  |  |
| Xindun | Beiguan | 15 | 270 | 4934.5 | 24 | 23 | 23 | 0 | 24 | 0 | 0 | 16 | 48 | 16 |
|  | Qingsong | 15 | 53 | 895 | 16 | 8 | 15 | 0 | 14 | 0 | 0 | 15 | 36 | 6 |
|  | Nanhua | 20 | 189 | 2271 | 20 | 15 | 18 | 0 | 26 | 0 | 1 | 20 | 44 | 11 |
|  | Total | 50 | 512 | 8100.5 | 60 | 46 | 56 | 0 | 64 | 0 | 1 | 51 | 128 | 33 |
|  | Per HH |  | 10.24 | 162.01 | 1.2 | 0.92 | 1.12 | 0 | 1.28 | 0 | 0.02 | 1.02 | 2.56 | 0.66 |

### 5.1.3  Income Recover

- According to the survey, the APs who have completed land acquisition, went to labor market for jobs by themselves after they received the compensation fees. There are at least 1 person of each HH has steady job position, and stable income. Income and living recover has gained attention. Interviews were conducted with Qingsong Village, Beiguan Village and Nanhua Village. Xin Dun town attaches great importance to the villagers’ employment training, which include welding, bricklaying, housekeeping and so on. There are 4 times trainings a year in each village, participating by more than 200 people/times. Affected households all have a stable work, with a monthly income of 2,000 yuan to 3,000 yuan. Interviews showed that the affected people have successfully completed the changes from rural to urban areas. Thanks to the construction of the new district of Zhangye City, a lot of employment opportunities have been provided, which enables all APs to find a new job in the city. Meanwhile, during the land acquisition process, around 35 to 40 mu lands each group are reserved for development. The developer provided 8000 - 5000 m2 commercial shops for each group. For example, in Group 4 of Qingsong Village, according to 50 m2 per person, averagely 230 m2 commercial shops are allocated to each HH, which can be used for renting, with a rent of 28 - 35 yuan per m2.

## 5.2    Sample Survey of Dingxi City

### 5.2.1    Design of Sample Survey

- There are 20 baseline sample survey HHs, and they are shown in table 5-6:

- Table 5-6    Baseline sample survey HHs

| Town | Village | HH |
| --- | --- | --- |
| Fengxiang Town | Bolin village | 20 |

### 5.2.2	Sample HH survey

- Survey results of income per capital of sample HHs are shown in Table 5-9. Sample HHs are located one village of one town, with an average population of 4.65 people and income per capita of 8,097yuan. Currently the arable land per capita is 2.2 mu.

- As of 31 October 2016, among the surveyed 20 sample HHs, there are 27 TV sets, 13 refrigerators, 20 washing machines, 0 tractor, 5 motorcycles, 0 pumps, 0 large livestock, 4 internet units, 36 telephones, and 11 cars.

- Wage accounts for 17% of total income of sample HHs, while family operating income accounts for 70%, and property income and transfer income account for 2% and 10% respectively. Among the expenditure of sample HHs, operating expenses account for 42%, while living expenses account for 50%. Sample HHs expenditure composition is shown in Table 5-8.

- Income and resource of sample HHs is shown in Table 5-9. For details of income and resource of sample HHs, please see annex 2.2.1. Family property situation of sample HHs is shown in table 5-10. For details of family property situation of sample HHs, please see annex 2.2.2.

- Table 5-7 Income composition of Sample HHs of Dingxi City(baseline survey)

| Category | Industry | Percentage |
| --- | --- | --- |
| Wage income |  | 17% |
| Family operating income |  | 70% |
|  | Primary industry | 70% |
|  | Secondary industry | 0% |
|  | Tertiary industry | 1% |
| Property income |  | 2% |
| Transfer income |  | 10% |
| Total income |  | 100% |

- Table 5-8  Expenditure composition of sample HHs of Dingxi City (baseline survey)

| Operation expenses | 42% |
| --- | --- |
| Purchase expenditure of fixed assets | 2% |
| Tax expenses | 0% |
| Living expenses | 50% |
| Property expenses | 1% |
| Transfer Expenditure | 5% |
| Total expenditure | 100% |

- Table 5-9  Income and resource situation of sample HHs of Dingxi City (per capital) (as of 31st October 2016)

| Town | Village | HH | population | Income |  |  | Before land acquisition |  |  |  | Land acquisition |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Agriculture | Working outside | Subtotal | Arable land | Dry land | Garden | Subtotal | Arable land | Dry land | Garden | Subtotal |
|  |  |  |  | Yuan | Yuan | Yuan | Mu | Mu | Mu | Mu | Mu | Mu | Mu | Mu |
| Fengxiang | Bolin | 20 | 93 | 45,000 | 708,000 | 753,000 | 224.2 | 0 | 0 | 224.2 | 0 | 0 | 0 | 0 |
| Per capital |  |  |  | 484 | 7,613 | 8,097 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 |

- Table 5-10 Family property situation of sample HHs of Dingxi City (as of 31st October 2016)

| Town | village | HH | Room | House area | TV | Refrigerator | Washing machine | Tractor | Motorcycle | Pump | Big living stock | Internet | Telephone | Car |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Unit | M2 | Set | Set | Set | Set | Set | Set |  |  |  |  |
| Xindun | Beiguan | 20 | 109 | 5,830 | 27 | 13 | 20 | 0 | 5 | 0 | 0 | 4 | 36 | 11 |
|  | Per HH |  | 5.45 | 291.5 | 1.35 | 0.65 | 1 | 0 | 0.25 | 0 | 0 | 0.2 | 1.8 | 0.55 |

### 5.2.3    Income Recover

- The income recovery plan of Dingxi City: pay the land compensation fees to affected HHs, and they develop Aquaculture. Some villagers also raise cattle. Since the land acquired villages are located at the subarea of Dingxi city, there are relative good job chances. All the HHs has one person work outside, with a monthly income of 3,000 yuan. Because of Aquaculture and working outside, the income level of the APs will not decline due to land acquisition. This method has been confirmed during the monitoring and evaluation investigation.

- The affected households will deposit the land compensation fee to bank for interest income. After land acquisition, the income compensation for these land-loss farmers is more than their income from the lands. Their living standard is recovered and improved, and can be fully guaranteed. The land-loss farmers take part in pension insurance, and can get pension after reaching the pension age.

- Meanwhile, Subsistence allowances are given to HHs with living difficulties. There are 120 HHs in Berlin Village enjoy this allowance, among which, 10 HHs enjoy class 1, 20 HHs enjoy class 2, 60 HHs enjoy class 3 and 30 HHs enjoy class 4. For class 1, the allowance is 140 yuan per person per month, for class 2 is 90 yuan per person per month, for class 3 is 60 yuan per person per month, and for class 4 is 50 Yuan per person per month. These people have stable income.

- For those who completed land acquisition, since they have received land compensation fee, their income has significantly increased. Combined with the increased employment opportunities because of urbanization, their income levels did not decrease due to land acquisition.

# 6    House Relocation

## 6.1    House Relocation of Zhangye City

- As of April 30, 2017, 185 HHs have finished house demolition, with an house area of 91,513 m2. All of the171 HHs have already moved into new houses. Part of them have several living places. The affected HHs are satisfied with the resettlement policy. House demolition progress of each village is shown in table 6-1.

- Resettlement houses of Beiguan village has been built up, and the affected HHs have moved in with satisfaction. Policies of resettlement houses in Beiguan village: (1) compensation is made according to Municipal Government’s house compensation policy. (2) the number of resettlement apartments is decided according to the composition of family members. And the areas of apartments are: 63, 83, 95.81, 104, 113.59 m2 respectively. When the child is over 12 years old, one additional apartment may be distributed to the family. (3) the price of resettlement house is paid according to the cost price: 1600 yuan/m2. (4) the house location is decided by a lot, with a mix first and fourth floor, third and sixth floor, and second and fifth floor. For house demolition situation, please see annex 2.1.3-1 and 2.1.3-2.

- Table 6-1  House demolition progress of each village(As of April 30, 2017)

|  | Planned |  |  | Actual |  |  | Percentage |  | Resettlement | Resettlement place | Completion time |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | HHs | population | Area | HHs | population | Area | HHs | Area |  |  |  |  |
| Beiguan | 82 | 321 | 39819 | 70 | 273 | 34322 | 85% | 86% |  |  |  |  |
| Nanzha | 32 | 125 | 15891 | 32 | 125 | 15,891 | 100% | 100% |  |  |  |  |
| Nanhua | 58 | 226 | 27301 | 50 | 187 | 24,465 | 86% | 90% |  |  |  |  |
| Qingsong | 31 | 121 | 14752 | 14 | 58 | 7114 | 45% | 48% |  |  |  |  |
| Liuquan | 2 | 8 | 1383 | 2 | 8 | 1,383 | 100% | 100% |  |  |  |  |
| Baita | 17 | 67 | 8338 | 17 | 67 | 8338 | 100% | 100% | In transition |  |  |  |
| Chengerzha | 68 | 238 | 24931.2 | 0 | 0 | 0 | 0% | 0% |  |  |  | Cancelled |
| Huaer | 10 | 43 | 3667 | 0 | 0 | 0 | 0% | 0% |  |  |  | Cancelled |
| Bayi | 12 | 45 | 4257 | 0 | 0 | 0 | 0% | 0% |  |  |  | Cancelled |
| Total | 312 | 1194 | 140339 | 185 | 718 | 91,513 | 59% | 65% |  |  |  |  |

- Note: for resettlement details, please refer to replies of memorandum.

- Eight (8) business operating HHs were demolished in Zhangye, with a house area of 273 m2. They are all well resettled. For the progress of affected self-employed HHs, please see annex 2.1.4.

- Due to the long period of City-villages involved in the transformation, and many influence factors, the house demolition is progressing relatively slowly. Some have direct impacted the construction progress of the project, and Xindun Town Government has given attention to this issue. Project Office of Zhangye City and Xindun Town Government are now researching seriously on the plan to enable demolition work progress in an orderly manner.

## 6.2    House relocation of Dingxi City

- As of April 30, 2017 , 289 HHs have completed house demolition, with a house area of 158,924 m2. Among them, 86 HH chose monetary compensation, 99 HHs chose property swap, and the other 104 HHs chose relocation in another site. Dingxi City Anding District Housing and Urban Construction Bureau signed compensation and resettlement agreements with the affected HHs. According to the assessment, both parties achieved agreements on the followings: construction structure, usage, construction area , ground attachments as well as the total evaluated compensation amount of the houses; the APs can choose the compensation method, namely, monetary compensation, property rights swap, and relocation, by themselves; relocation period, disbursement of funds, handover of resettlement apartments, cancelling of certificates, and breaching of contract, etc.; for monetary compensation, 10% extra will be paid based on house and attachments as rewards; homesteads shall be compensated according to 90 yuan per m2; for property swap, housing construction area of property swap is based on the current status, with independent property rights, and the ratio of property swap shall be determined according to the policies. It shall be calculated based on the selected house area. Relocation: if the initial house demolition area is more than the area of assigned homestead, the exceeding part shall be compensated according to 90 yuan per m2. For residential housing resettlement, please see table 6-2 and 6-3. For shops resettlement, please see table 6-4. For sampling investigation results, please see table 2.2.4.

- Because of the adjustment of the plan, Anjiazhuang kindergarten, which needed to be demolished in the original plan, does not need to be relocated any more.

- Table 6-2 Residential Resettlement (1)

|  | Plan |  |  |  | Actual |  |  | Percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Resettlement methods | Resettlement plan |  |  | Resettlement sites | Resettlement plan |  |  |  | Resettlement site |
|  | cd1,cd3,cd4 | cd5,cd6 | Subtotal |  | cd1,cd3,cd4 | cd5,cd6 | Subtotal |  |  |
| Monetary compensation | 25 | 14 | 39 |  | 19 | 67 | 86 | 221% |  |
| Property swap | 25 | 52 | 77 | Yangguang xinyuan Community | 29 | 70 | 99 | 128.6% | Yangguang xinyuan Community |
| Relocation | 75 | 8 | 83 | Bolin Village centraliyed resettlment site (Momoujiaping) | 35 | 69 | 104 | 125.3% |  |
| Subtotal | 125 | 73 | 198 |  | 83 | 206 | 289 | 146.0% |  |

- Table 6-2 Residential Resettlement (2)

|  |  |  | Measurement |  | Actual |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual |  | HH | Area | Area | Agreements completed | Demolition completed | Resettlement completed | monetary | property | Relocation | Subtotal | Remark |
|  |  |  | HH | M2 | M2 | HH | HH | HH | HH | HH | HH | HH |  |
| cd3,cd4 | Xihuan Rd. | Bolin Village | 45 |  |  | 45 | 45 | 45 | 14 | 16 | 15 | 45 | (Cheng An has appealed to the court and is expected to be resolved in June 2017.) |
|  |  | Xiershilipu | 8 |  |  | 9 | 9 | 9 | 3 | 3 | 3 | 9 |  |
|  |  | Ershipu | 8 |  |  | 8 | 8 | 8 | 2 | 2 | 4 | 8 |  |
|  |  | Subtotal | 61 | 36,561.04 | 30,733.61 | 62 | 62 | 62 | 19 | 21 | 22 | 62 |  |
| cd1 | North Dingxi Rd. | Bolin Village Yuejiazhuang Group | 8 | 4,426.07 | 4,426.1 | 8 | 8 | 8 | 2 | 3 | 3 | 8 |  |
| cd1 | Middle Beian Rd. | Bolin Village Anjiazhuang, Jiujiazhuang. | 13 | 8,976.32 | 8,976.3 | 13 | 13 | 13 | 4 | 5 | 4 | 13 |  |
| cd5,cd6 | Jiaotong Rd. | Bolin Village | 136 |  |  | 174 | 174 | 174 | 49 | 60 | 65 | 174 | (Including 67 shops). 4 shops (Jihong Ma, Yuhong Ma, Youming Feng and Shehuo Association of Bolin Village) did not achieve agreements. |
|  |  | Beiershipu | 27 |  |  | 29 | 29 | 29 | 9 | 10 | 10 | 29 | Chenglong Zhang did not achieve agreement. |
|  |  | Donghe Village | 1 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 1 |  |
|  |  | Subtotal | 164 | 81,169.71 | 113,789 | 204 | 204 | 204 | 59 | 70 | 75 | 204 |  |
| cd5,cd6 |  | Bolin Village Majiazhuang Community | 2 | 999 | 999.0 | 999.0 | 2 | 2 | 2 | 2 | 0 | 0 | Yilian |
| Total |  |  | 248 | 132,132.14 | 158,924 | 289 | 289 | 289 | 86 | 99 | 104 | 289 |  |

- Table 6-4 Progress of shop resettlement

|  |  | Plan | Actual |
| --- | --- | --- | --- |
|  |  | Shops | Shops |
| HH | HH | 67 | 67 |
| Persons | Persons | 296 | 296 |
| Color steel | M2 | 4513 | 4513 |
| Brick concret | M2 | 21658.48 | 21658.5 |
| Brick wood | M2 | 1891.04 | 1891.0 |
| Subtotal | M2 | 28062.52 | 28062.5 |
| Simple structure | M2 | 910.57 | 910.6 |
| Shed | M2 | 2373.4 | 2373.4 |
| Sunshine tile | M2 | 0 | 0 |
| Storage house | M2 | 1245 | 1245 |
| Civil wood | M2 | 0 | 0 |
| Sunshine room | M2 | 0 | 0 |
| Walls | m | 840 | 840 |
| Kennels with steel net | Unit | 4 | 4 |
| Well | Unit | 1 | 0 |

# 7   Restoration of infrastructure

## 7.1     Infrastructure of Zhangye City

- As of April 30, 2017,the infrastructure in new district is under construction.

## 7.2    Infrastructure of Dingxi City

- As of April 30, 2017, since infrastructure has not been affected by the progress of project construction, the infrastructure within the project area can still work normally.

# 8    Resettlement Fund

## 8.1    Resettlement Fund of Zhangye City

- Land acquisition and resettlement fund is raised by Zhangye Municipal Land and Resources Bureau. Currently land acquisition and resettlement fund can meet the requirements of project construction on land acquisition and resettlement. As of April 30, 2017, a total amount of 140,663,097 yuan has been paid as land acquisition and housing relocation fees for the road network project subprojects, accounting for 52.69 % of the total resettlement budget. As of April 30, 2017, the implementation unit has paid land acquisition and house relocation fees to the APs. Resettlement funds for the Road network engineering subproject are shown in Table 8-1. Because the land compensation standard is higher than the RP standard, so the actual land compensation fee is more than the planned amount.

- Table 8-1  Zhangye Municipal Resettlement Fund

- (As of April 30, 2017) Unit: yuan

|  | Planned | Actual | Actual percentage |
| --- | --- | --- | --- |
| 1. Land compensation | 56,739,381 | 68,893,605 | 121.42% |
| 2. House compensation | 56,757,689 | 53,235,880 | 93.80% |
| 3. Special compensation for restoration and reconstruction | 27,354,832 | 16,220,013 | 59.29% |
| 4. Management fee | 2,817,038 | 2,213,599 | 78.58% |
| 5. Other fees | 88,485,810 | 100,000 | 0.11% |
| 6. Contingency | 34,823,213 | 0 | 0.00% |
| Total | 266,977,963 | 140,663,097 | 52.69% |

## 8.2    Resettlement Fund of Dingxi City

- Land acquisition and resettlement fee is raised by Dingxi Urban Investment state owned Assets management Ltd. Currently the capital can meet the demand from engineering construction to land acquisition and resettlement. As of April 30, 2017, in total 279,892,183yuan were paid, which accounts for 69.21% of the total budget. For Dingxi City Resettlement Fund, please see table 8-2.

- Table 8-2 Dingxi City Resettlement Fund (As of April 30, 2017)

|  | planned |  |  |  | actual |  |  |  | percentage |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contract package batches | first batch | second batch | third batch | subtotal | first batch | second batch | third batch | subtotal |  |
| 1. land compensation fee | 9231810 | 37202034 | 7684453 | 54118297 | 9,231,810 | 28,328,419 | 19,464,929 | 57,025,158 | 105.37% |
| 2. house compensation fee | 0 | 108695345 | 187164279 | 295859624 | 0 | 30,000,000 | 192,867,025 | 222,867,025 | 75.33% |
| 3. schools | 0 | 1371857 | 0 | 1371857 | 0 | 0 | 0 | 0 | 0.00% |
| 4. vonarable subsidy | 100000 | 100000 | 100000 | 300000 | 0 | 0 | 0 | 0 | 0.00% |
| 4. mangagement fee | 466590 | 7368462 | 9747437 | 17582489 | 0 | 0 | 0 | 0 | 0.00% |
| 5. unforseeable fee | 933181 | 14736923 | 19494873 | 35164977 | 0 | 0 | 0 | 0 | 0.00% |
| Total | 10,731,581 | 169,474,621 | 224,191,042 | 404,397,244 | 9,231,810 | 58,328,419 | 21,233,1954 | 279,892,183 | 69.21% |

# 9    Participation and information disclosure

## 9.1    Participation and information disclosure of Zhangye City

- public participation is emphasized by the implementation unit during physical volume investigation and land acquisition. Several meetings were held to publicize the policies of land acquisition and house demolition of this project. For the transformation of city-villages policies, which affect all the villages, there is a full public participation. Each household has the right to voice their opinions, and so do the housewives. The resettlement policies for city-villages are made after all the village groups have reached a consensus. Due to the complexity of the transformation of city-villages, it takes a long time to resolve this issue.

- By each monitoring, the resettlement experts group visited the project area, conducted interviews in affected towns, examined the progress of the resettlement work, interviewed grassroots cadres, and listened to attitudes and opinions on immigration and resettlement work of the AHs.

## 9.2    Participation and information disclosure of Dingxi City

- Public participation is emphasized by the implementation unit during physical volume investigation and land acquisition. Several meetings were held to publicize the policies of  land acquisition and house demolition of this project.

- During the monitoring and evaluation, resettlement experts group visited the project area, conducted interviews in affected towns, examined the progress of the resettlement work, interviewed grassroots cadres, and listened to attitudes and opinions on immigration and resettlement work of the AHs.

- Extensive public participation during the house measurement has received a certain effect. On March 10, 2016, Dingxi City investment company held its 3rd meeting on Dingxi Demolition leading group for urban road construction, and the main issues discussed are: (1) relocation issues. Within the house demolition area, for HHs who chose relocation voluntarily,  they shall be resettled unified in Mojiaping Resettlement site, and the specific resettlement program shall be determined by the District Housing Construction Bureau, for those who will resettle in the original plan area, the house shall be built according to the original design, for those who will resettle in the new plan area, the house shall be built according to the new designed plan. District Housing Construction Bureau shall be responsible for the Water, electric power supplies and roads, as well as the site preparation of the resettlement site, while the expenses shall be taken by Dingxi City Investment Company. Dingxi City Investment Company and District Housing Construction Bureau shall assign some professional and technical personnel to take charge of land allocation, actinomycetes, and to track, guide and supervise the house construction of each HH to ensure that the construction standards are in line with the design requirements. (2) resettlement apartment cost verification issue. Property swap houses of this project are all located in Yangguang Xinyuan Community, verified by Price and other related departments, the cost of resettlement apartments is 3350 per m2. For affected HHs, who choose property swap voluntarily, and the actual exchange house area is under 300 m2, the area difference between actual area and 300 m2 shall be compensated to the affected HHs according to cost price; if the affected HHs need a house area of more than 300 m2 due to housing requirement, and they are willing to pay the exceeding area, they shall pay the area within their compensation range according to cost price, and the exceeding area according to market price. (3) Sale and accreditation issues of resettlement apartments. For affected HHs, who choose property swap and want to sale the resettlement apartments voluntarily, City Investment real estate company and House Demolition Office shall take charge of the agreements rename formalities for affected HHs who are active and initiative during the house demolition. (4) Monetary compensation and resettlement issues. During the implementation process, specific comparisons were carried out for the three compensation schemes(cash compensation, property swap and relocation). There is some gap between monetary compensation and the other two schemes, which need to be further improved. Opions of affected HHs were widely asked, and appropriate adjustments were made for monetary compensation scheme. For affected HHs who choose the monetary compensation, 10% is added  the compensation based on the total compensation amount.

- ADB loans road construction project house demolition office issued to each household " housing demolition notice on the ADB loan road construction project of Dingxi City Anding District Municipal People's Government" and defined: demolition scope, deadline of agreement signing, and location of agreements signing. For solutions to the recent complaints about Dingxi Project, please refer to Table 9-1.

- Table 9-1 Solutions to complaints about Dingxi Project

| Name | Complaints | Solutions | Results |
| --- | --- | --- | --- |
| Xiaoming An | After the signing of the ADB project contract, there are disputes about the “An Ding District Bureau of Law Enforcement Comprehensive Security Executive Letter (2016) No. 10”. | After several consultations between the City Investment, as well as Director and Bureau of Law Enforcement, Xiaoming An explained that the illegal construction was built by other people, who rented this land, and agreed the later part of the payment to be paid out. | Xiaoming An was very satisfied. |
| Yuming Ma | On May 5, 2016, he refused to sign the contract due to the very few choices of apartments, and good floor have been all selected. | Comprehensive Director Jianjun Wang, area responsible person of Fengxiang Town, as well as Qiaozhen Xiao, deputy director of the Urban Construction Bureau connected with City Investment, and opened on May 20, 2016 a new building with112 sets of apparments. | Yuming Ma was very satisfied and signed the contract on May 7th, 2016. |
| Hongming An | On September 9, 2016, it was reflected that the “three supplies and one leveling” in Moujiaping Phase II Place Ten was not in place, affecting the APs to choose homestead for resettlement, who have already signed the agreements. | Comprehensive Director Jianjun Wang, area responsible person of Fengxiang Town, as well as Qiaozhen Xiao, deputy director of the Urban Construction Bureau connected with City Investment, and City Investment consulted several times with Municipal Government. On september 20, 2016, “three supplies and one leveling” at the resettlement point are in place, and on September 21st, all the homesteads for the affected HHs, who have already removed, were allocated. | The homesteads were all allocated in place, and the HHs who has signed the agreements, were all very satisfied. |
| Jin Yue | On April 25, 2016, remote replacements in Moujiaping have been signed, but the household Jin Yue wanted more remote resettlement sites becaue of family split. | Comprehensive Director Jianjun Wang, area responsible person of Fengxiang Town, as well as Qiaozhen Xiao, deputy director of the Urban Construction Bureau connected with City Investment, and City Investment consulted several times with Municipal Government. On May 4, 2016, the land of Moujiaping Phase II was developed, so that the ADB project can be conducted smoothly. | Jin Yue showed a very good understanding and satisfaction with the solution to the demolition, and signed the contract on May 9, 2016. |

# 10    Organization and Management

## 10.1    Organization and Management of Zhangye City

- The main organizations concerned resettlement of this project includes: (1) ZGDFLMC, (2) Resettlement Division (PRO) of ZGDFLMC, (3) Zhangye Land Resources Administration Bureau, (4) Xindun Town Government, (5) All related Village Committees, and (6) External Monitoring Organization of Resettlement. Resettlement agency responsible by Zhangye City owns a wealth of experience. All the organizations are operating normally.

## 10.2    Organization and Management of Dingxi City

- The main organizations concerned resettlement activities of this project include: (1) Anding District Resettlement Leading Group, (2) Foreign Loan Office of Dingxi Finance Bureau, (3) Dingxi Urban Construction & Investment and Asset Management Ltd Co., (Dingxi ADB Project Management Office), (4) Anding Urban Construction Bureau, (5) Dingxi Land Resources Administration Bureau, Anding Branch, (6) Anding Urban Housing Demolishment Office, (7) Township Resettlement Group, (8) Village Committee Resettlement Group, and (9) Independent External Monitoring and Evaluation Institution. Resettlement agency responsible by Dingxi City owns a wealth of experience. All the organizations are operating normally.

# 11    Monitoring and Evaluation

- Resettlement Division (PRO) of ZGDFLMC, Xindun Government  and village committees established internal monitoring system of Zhangye City.

- Resettlement Division of Dingxi Urban Construction & Investment and Asset Management Ltd Co., Dingxi Relocation Company and village committees (communities) established internal monitoring system.

- Shanghai Yiji Construction Project Consulting Co. Ltd. Conducted external independent monitoring and evaluation for the resettlement of this project. Eight resettlement monitorings were completed up to this report period.

# 12   Conclusions and Suggestions

## 12.1    conclusions and suggestions of Zhangye City

### 12.1.1    Conclusions

- (1) Currently there are some broken roads, affecting the effectiveness of the project.

- (2) The land acquisition and demolition restricts the implementation progress of this project.

- (3)  Zhangye City attaches great importance to the training of affected households, the affected people have completed the conversion from farmers to urban residents, and their livings are stable.

- (4) Great importance has been attached to the contents of the recovery section of the memorandum and most tasks of land acquisition and resettlement have been completed.

### 12.1.2    Suggestions

- (1)  Speed up the follow-up of the judicial process.

- (2)  Increase resettlement funds for compensation, and promptly deal with problems arising from land acquisition and resettlement.

## 12.2    conclusions and suggestions of Dingxi City

### 12.2.1   Conclusions

- (1) The land acquisition and demolition has made great progress, and the work is very effective.

- (2) Compensation for illegal constructions were given  in accordance with policies and provisions, with a relative good treatment effect.

- (3) The ability of people engaged in the land acquisition and house demolition work is good. It is not easy to complete such a heavy task of land acquisition and house demolition in such a short time. Currently there are only 6 HHs with house demolition problems.

### 12.2.2   Suggestions

- (1)  For APs who resorts to Court, the adjudication of Court shall be implemented, .

- (2)  For those who have not signed an agreement yet, further work shall be done for them, in order to resolve the issue as soon as possible.

- (3)  Speed up the settlement of the houses demolition problems of the 6 HHs.

# Annex I   Interviews

## 1.1    Interviews of Zhangye City

April 24, 2017 Xindun Town   Haidong Wang

Zhaowu Road project is cuurently not plan to be carried out. Gaotai Road completed a

third of the housing agreement negotiations, and is expected to be completed by

the end of 2017. Three appealed HHs in South Linze Road have signed the compensation agreement, the houses have been demolished, and the road is under construction. There is still some land acquisition and demolition work not completed, which is expected to be finished end of this year. For the income recovery of the APs, we have given attention. The government allocated development of land for each group, using for shops to improve the non-agricultural income sources of these villagers.

Note: the bellowing interviews are before this monitoring and evaluation.

October 8, 2016 Xindun Town   Mingfu Zhang  Governor of the Town

We attach great importance to ADB loan projects. Currently the issues are all difficult problems, and we will try to find solutions.

October 8, 2016 Qingsong Village   Wei Wang  Secretary

Compensations for land acquisition have been all paid out. People have a stable living with an increased income. The main income sources are working outside, operating catering, residential property services, and car repairs. The income is variable among people, generally with a monthly income of 5,000 to 1,000 yuan. Government attaches importance to employment, and trainings are often organized. This year, 6 times trainings were organized, with a participation proportion of 10% to 20%. The villagers mainly complained that the compensation standard is too low. If the attitude is lowered, then the complaint would be less. There are big changes in Qingsong Village in recent years, which is recognized by the villagers. The village has a population of 2060 people, and there are 370 mu of lands left. The reported net income per capita of the farmers is 10,400 yuan. There are 11 low income HHs enjoying the allowances.

Because of compensation standards, a pig farm and a small forest have not achieved agreements. We are currently doing negotiation work.

October 8, 2016 Beiguan Village   Director Xing Deng

The land acquisition and house demolition in Beiguan Group 1 has not started yet, and it is mainly because of the government. Beiguan Group 1 has only a few lands, but many houses are within the demolition scope. I hope the government can start the land acquisition as soon as possible. Government has always attached importance to the training of farmers, which are organized 4 times a year, with 30 participants each time. The main contents of training include catering, shelf work, bricklaying, and welders. There are 16 low-income households in the village, and they all receive subsistence allowances. Currently the big problem is that there is no road.

October 8, 2016 Nanhua Village   Director Xinhong Chen

The resettlement buildings for North Gaotai Road are not finished, mainly for Nanhua Village Group 9, with more than 300 persons. Some residents received the apartments in September this year, and are currently decorating. 65 families will demolish this year, and the demolition will be completely finished until march next year. There are people working outside in each HH, with a monthly income of more than 3000 yuan. Xindun town organized trainings, mainly are trainings for shelf working, bricklaying, and catering. More than 200 people participated in the trainings. The village has a total population of 2700 persons, and there is no minority. There are 10 low-income HHs, and they all receive subsistence allowances. Now the compensation standard is low, but there is no other way. The net income per capita of the village is 9,000 yuan.

March 30, 2016 Xindun Town   Section Chief Hu

Houses in Zhaowu are not demolished yet, since the people here have high demands. It could be difficult. Houses of Nanhua Group 9 are not demolished, and the resettlement buildings are completed. Yet the compensation fund is not in place, which has affected the progress. It is expected to be finished in October 2016. In Nanhua street for a pig farm, there is big price difference between the evaluation price and the affected HH, and the judicial process is carrying on. Resettlement buildings for Qinsong Village Group 5 and 6 are completed, but due to fund issue, the houses are not demolished yet. Currently there are two time spots for ADB project, one is in October 2016, the other is in December 2016.

4 November 2015, Minghu Zhang, Governor of the Town

There are 500 meters on Zhaowu Road, which needs big amount of demolition. There are 96 residential HHs, plus shops, in total 120 households. The demolition is too big, and the

compensation expectation of the villagers is also very high. We can only wait (for the developer).

65 HHs of Group No.9 Nanhua Village on North Gaotai Road is also not demolished, and the resettlement building is not completed yet, it is estimated to be finished in June 2016.

North third Ring and Juyan Road are already open to traffic.

The house demolition of 10 HHs of Group No.9 Nanhua Village on West Linsong Street is not completed.

4 HHs of Group No.8 Xiguan Village on East Linsong Street are taking the judicial procedure.

Two HHs of Baita Street need to take the judicial procedure.

5 HHs of South Linze Road need to take the judicial procedure.

1 pig farm of Nanhua Street does not agree with the evaluation, and needs to take the judicial procedure.

In October 2015, Yuguan Road is open to traffic.

In general, the land acquisition is basically completed, however, there are still some problems on house demolition and the construction progress of resettlement buildings. Further work need to be done.

4 November 2015, Caixia Zhang, Governor of the Town

Since there are 500 ancient trees on Wenchang Road (Xuefu Road), the rerouting is needed for the protection of the trees. It is 900 meters long from south to north, involving Group No.1 and No.2 of Beiguan Village. The land acquisition is completed and the same policy as in the RP is implemented. There is no more demolition for Group 1, while two HHs need to be demolished for Group 2. In Spring next year (2016), the renovation of “Village in the City” will be carried out for Group 2 of Beiguan Village.

On these lands, with the cooperation between the government and Zhangye North Bay real estate company, the construction is expected to start before May 1, 2016. Because the location of the lands is good, the real estate development companies are very active, and the residents are willing to relocate. Therefore, there should be no big difficulty. We will do a good job for the compensation plan in winter. There are 400 persons in Group 2 of Beiguan Village, with 200 mu arable lands. The main source of income is working outside as migrant workers, with a monthly income of 3500 yuan.

4 November 2015, Bieguan Village, Director Xing Deng

There are 1,860 people in our village, with 546 HHs and four groups, 100 mu lands. The net income per capita is 8,500 yuan. There are minority women married to my village. There are 43 HHs with subsistence allowances, which are 70 people, and the guaranteeing fees are transferred directly to their cards. There are no remaining issues for the land acquisition. Since there are ancient trees, Wenchang Road was rerouted, occupied the land from Group 1 and Group 2. More lands are occupied in Group 2 than in Group 1.

Consultation has been conducted with the villagers for the road rerouting, and in total five meetings were held. By the end of 2016, the land acquisition and housing relocation problems of Wenchang Road will be resolved. Special persons from Government are responsible for it. The income source of the villagers is working outside. The income of the sample household in the report was too high (from the actual).

4 Nov. 2015 Qingsong Village, Director Jibin Sun

There are 515 HHs in the village, with 1980 people. The income per capita is 9,256 yuan, and there are no minorities in the village. We have 31 Guaranteeing HHs, with 45 persons. The monthly subsidy standards are divided as follows: the fourth category: 60 yuan, third category: 90 yuan, second category: 234 yuan, and the first category: 275 yuan. The subsidy is guaranteed. On average, each household has two apartments, with an area of about 100 m2 each, and the apartments are sold at cost price to the villagers. The price for the first and second floor at A District is 1300 yuan / square meter, while the rest is 1350 yuan / square meter. The villagers are basically satisfied with the resettlement. The main source of income is working outside. Trainings, such as: cashier, hotel staff, scaffolders, bricklayers, Electric welders, also regularly organized by the Government. There are more than 20 times training each year, with more than 20 participants each time, and in total about 500 people were trained, among which, 40% of them are women, and 90% of them have found a job. Certificates are issued to qualified participants of the trainings.

04. Nov. 2015 Nanhua Village, Director Xinhong Chen

There are 680 HHs in the village, with 2700 people. There is no minorities in the village.

The net income per capita is 9,000 yuan. There are 10 HHs with subsistence allowances. We have 11 groups in the village. The construction and distribution of resettlement buildings for Group 2 and 6 is completed, while the roof of resettlement building for Group 10 is almost sealed. The resettlement buildings for group 4, group 7, group 8, and11 is under construction, while for group 1, group 3, group 5 and 9 is not started yet.

The income source of the residents is working outside. There are trainings each year, which include trainings for Electricians, scaffolders, and catering. 5 trainings were held from 2014 to 2015, with 100 participants each time, and 500 persons in total. There is no problem for land acquisition, but some issues for house demolition. We will try to solve them next year.

14 April 2015, Minghu Zhang, Governor of the Town

Beginning late last year, our town tried hard to do a good job in house demolition. For Example, 50 HHs demolition completed in Group 3 of Qingsong, 49 HHs demolition in Group 4 of Qingsong 103 HHs demolition in Group 6 and 7 of Xiguan, 34 HHs demolition in Group 4 of Nanza, 46 HHs demolition in Group 3 of Huaer, and 48 HHs demolition in Group 4 of Beiguan. The main task is to prepare the people for house demolition, and we started at 8:00 am every day. We achieved some success. The most difficult problem currently is the construction fund. The transition period of the people is very important, and we also pay great attention to it. I hope the Government can strengthen the financing of housing demolition funds to accelerate the construction progress of New Area.

14-16 September 2014 Minghu Zhang  Governor of the Town

The land acquisition work is progressing smoothly, but the resettlement house building is relatively slow, mainly because the land acquisition for resettlement relates to interest, and takes time. Now since the building of resettlement sites is slow, the project construction is seriously affected. We are now doing the coordination work, it will be definitely solved finally.

Last time we reported that 5 HHs hope to raise the compensation standard. Now through coordination work, they signed the land acquisition agreements.

15 September 2014 Qingsong Village Zheng Zhang

There are 6 people in my family, and the current area for new apartment is 95.5 m2. Before we had 8 mu land, and the land compensation is 88,000 yuan / mu. We received all the compensation fee. Our original house occupied 400 m2, with a construction area of 300 m2, and they are all legal constructions. We received 4 apartments, among which, 3 are 90 m2, and one is 110 m2. There are people living in these 4 apartments. We are satisfied with the house resettlement. Our main income source is now working outside, and we also plant some vegetables. We can get pension after we reach the age. 200 m2 shop room is distributed to us, and now the monthly rent is 30 yuan/m2, with a monthly rent income of 6000 yuan. The price for new apartments is 1300 yuan/m2. We used part of the land compensation fee for purchasing the new apartments. We can adapt ourselves to the resettlement apartments. We are living very well now.

15 September 2014 Qingsong Village Fugui Xie(vulnerable Group)

There is one person in my family. All the land and house were acquisitioned. I had 3.6 mu land, and 1 mu land was compensated with 68000yuan/mu, among which, 18000yuan/mu for young crops. I received all compensation fee. The original house was 160 m2. This time two sets of apartments were distributed to me, with 130 m2. I am now living in one of the apartment, and rented the other one out. Now I have also low-income subsidy. Before I had an annual income of 10000 yuan, and the current income has been greatly increased compared with the one before.

15 September 2014 Qingsong Village Secretary

Our village built Qingsongjiayuan A district, with 13 buildings (10 floors), among which, 5 are resettlement apartments, and 5 are commercial apartments. Meanwhile there are also shop rooms. The commercial apartments are built along the street, and the supporting infrastructure is under construction. It is estimated to be completed next year.

14 September 2014 Nanhua Village Xinhua Chen Director

There is still no land acqusition in our Group 1, and 100 mu land are left in Group 5, whereas the other land compensation has been completed. Pension has been already implemented after land acquisition. For villagers older than 17, the government pays 60%, and the individual pays 40%. Last year it is 17000 yuan/person, and this year it is 27000 yuan / person. For men older than 60 and women older than 55, they can receive 900 yuan / month. The compensation fee after land acquisition is distributed per capital. Group 2 is 180000yuan/person, Group 3 is 140000yuan/person, Group 4 is 140000yuan/person, Group 5 is 90000yuan/person, Group 6 is 120000yuan/person, Group 7 is 150000yuan/person, Group 8 is 250000yuan/person, Group 9 is 160000yuan/person, Group 10 is 150000yuan/person, and Group 11 is 130000yuan/person. This is in general fair. After receiving the land compensation fee, all APs work outside, mainly at the new district, with a stable income. Nowadys in Zhangye City, if you want to work, then you will find a job position. House resettlement implemented plan, divided into a, b, and c district. District b is built for village committee and woodland. District A has finished the roof, and is for Group 2, 6 and 9. District C is still in planning. House compensation is according to the standard of the district, and the new apartment is according to the cost price, which is 2000 yuan/m2. The villagers hope the compensation standard can be higher, but the Government has its difficulty.

14 September 2014 Qingsong Village Jibin Sun Director

Group 1-4 in our village have completed land acquisition, while there are still 50mu, 30 mu, more than 200mu and 200 mu left in Group 6,7,8 and 5 respectively. The final land acquisition time for Group 1 is on 31. August 2013, and the standard is 88000yuan/person, while the final land acquisition time for Group 2 is on 31. October 2013, and the standard is 130000yuan/person, the final land acquisition time for Group 3 is on 31. October 2013, and the standard is 70,000 yuan/person, the final land acquisition time for Group 4 is on 30. October 2013, and the standard is 150,000 yuan/person, the final land acquisition time for Group 5 is on 30. April 2008, and the standard is 60,000 yuan/person, the final land acquisition time for Group 6 is on 30. June 2008, and the standard is 65000yuan/person, the final land acquisition time for Group 7 is from 2004 till now, and the standard is 100,000 yuan/person, the final land acquisition time for Group 8 is in 2010, and the standard is 5000yuan/person (land acquisition just started). 95% of the land compensation fee is distributed to the villagers, while 5% is distributed to village committee for handling related procedures.

After receiving the land compensation, they are work outside. Mostly are in the local districts.

House resettlement: Group 5 and 6 are resettled at Ninghe Garden ditrict a, and people moved in in 2009, with an area of 100 to 120 m2. Group 7 moved into district and built 2 buildings. Group 1 and 8 are resettled at Qingsongjiayuan district b building No.1 and 2, which are constructed in 2014 and now the main body is finished, and can be finally completed in August 2015, with an apartment area from 100 to 118 m2. The resettlement building for Group 2 is not constructed yet. Group 3 is resettled at Qingsongjiayuan district b building No.3-8, which are now under decoration. Group 4 is resettled at Qingsongjiayuan District a building No.1-5, which are now under decoration and can move in at the end of the year, with an apartment area of 120 m2, 112 m2, and 100m2 and 90 m2. Building No.1 and 2 are tall buildings, whereas building 3-5 are 6-floor buildings. The building quality is good, and people are satisfied. There are complete facilities.

14 September 2014 Beiguan Village Yongchao Hu, Xuehu Tian

There is one group in Beiguan Village which has no land acquisition, the others are all completed. There are 7 groups. Group 2 is 65000yuan/person, Group 3 is 78000yuan/person, Group 4 is 68000yuan/person, Group 5 is 58000yuan/person, Group 6 is 68000yuan/person, Group 7 is 80000yuan/person.

14 September 2014   Lijuan Zhu

The land compensation fee is 40000 yuan/person, and the land acquisition is not completed yet. I agree with land acquisition. I bought an apartment at Beiguanjiayuan, with an area of 95.8 m2. The price is 1680 yuan/m2, with 3 sleeping rooms and a living room. My old house is not demolished, and I am satisfied with land acquisition.

14 September 2014   Feng Zhao

I have received the land compensation fee. I am not so clear how much I received. I bought an apartment in Beiguanjiayuan(104m2), with 3 sleeping rooms and 2 living rooms. The price is 1680yuan/m2. There are 4 people in my family. We are satisfied with the land acquisition.

Photo 1: house before resettlement

Photo 2: Qingsong community in construction

21 May 2014 Minghu Zhang Governor of the Town

Land acquisition is relative smooth, and the compensation fee for completed land acquisition is already paid out. But the house resettlement progress is relative slow, and the main reason for that is the approval of house building plan needs much time. We have made resettlement time table for each village, and will try the best to accelerate house construction progress.

21 May 2014 Yi Zhang, Secretary of Nanhua Village

Only No.11 Group in our village has not completed land acquisition, the others have all completed. The land compensation fees have been paid all to villiagers. The farmers take part in pension insurance, and can get 745 yuan per month after reaching the retirement age. There are relative plenty of job opportunities. 20% of the villagers can make small shops, with monthly income of 10,000 yuan, Other villagers (60% of the villagers) who work outside can earn 3,000 yuan per month. The rest 20% receive pension. In general, we are satisfied. For the people with living difficulties the government issues subsistence allowances, with standard of 90-300yuan per month, and in together 86 persons are enjoying this. Five Guarantees HHs get 200 yuan per month. Land compensation fee is 66,000 - 68,000 yuan/mu.

20 May 2014 Zhengfeng Ma, Director of Ganzhou District Land and Resource Bureau

ADB Load Road Construction related land use procedures are all completed. District Land and Resource Bureau signed land use agreement with People Government of Xindun Town, and paid land compensation fee according to the agreement. Currently the progress is smooth. Same as other places, the APs have always some opinion about land acquisition, and the town has done much work for that. The Town Government is responsible for the resettlement building construction, and the village committee is in charge of implementation.

9th October 2013 Minghu Zhang Governor of the Town

Land acquisition of ADB loan project is processing in order. Compensation fees are paid by District Land Bureau directly to the Xindun Town, after the distribution plan is discussed and decided by the villages and groups, the town government paid compensation directly to villagers.

XinDun Town regulates that each villager group has 45 mu lands for roads use, with a compensation of from 21,000 yuan / mu to 22,000 yuan / mu. For Lands over 45 mu, the compensation is from 60,000 yuan / mu to 78,000 yuan / mu. This provision is recognized by everyone. Government formulated the rules for landless peasants’ pension and insurance policy. For people who participate in pension and reach the age, they can receive 610 yuan per month. We can actively participate in pension insurance. There are a lot of working opportunities in Zhangye City, with a daily wage income over 100 yuan, while the persons with skill can earn more than 200 yuan a day.

Housing compensation standard is raised up by about 20% based on the provisions of Municipal Government. Residents purchase resettlement house at cost price, and the standard is 1600 yuan / square meter. Resettlement community of Beiguan Village has been completed, whereas the community for Nanhua Village will start to construct in March next year. The demolished HHs are in transition period, and we paid for transition costs.

Among the land acquisitioned HHs, there are 5 HHs who have not received land compensation fee. They think that the compensation is too low. We are doing the work.

It is recommended that each group should have 15 mu land for resettlement, each HH has 40-50 m2 business room, and two apartments to solve the evicted worries of the demolished HHs.

9th October 2013 Rong Qi  No.3 Group Beiguan Village

I am engaged in construction, with an annual income of 200,000 yuan. Houses were demolished last year, and the house compensation fees are 160,000 yuan, which I have already all received. We are allocated in Beiguan Community, with three housing units, two small and one large set, with a total area of ​​210 m2. The resettlement house price was 1600 yuan / square meter. There are 13 buildings in Beiguan Community, with 400 housing units. Residents of Group 3 and 5, 6, and 7 are relocated to this area. There are 60 business rooms. Land compensation standard is 78,000 yuan / mu, and is distributed per capita. Land compensation fee is distributed within the whole group averagely; my family received 800,000yuan. My wife works in the supermarket, with a monthly income of 1,500 yuan. We have two children. My parents both participated in peasant’s pension insurance. We are satisfied with the land compensation and resettlement policy.

9th October 2013 Zongyu Zhao No.3 Group Beiguan Village

Land compensation is allocated averagely based on more than 130,000 yuan per capita. There are 6 people in my family, and we received all land compensation fees. Our old house was more than 300 m2, and we received all the 150,000 yuan compensation fees. We got 2 sets of apartments, with more than 200 m2. We bought it at the cost price of 1600 yuan / square meter. I attended the landless peasants’ pension insurance. Children are working, with stable income. We are satisfied with the policy.

9th October 2013 Xueshun Shao No.7 Group Beiguan Village

Land acquisition has been finished, and the compensation is distributed according to 156,000 yuan per capita averagely. There are 6 people in my family. A number of meetings were held for land compensation and resettlement issues, and at least one person of each family attended. All received land compensation. Compensation of 100000 yuan was paid for my old house, and there are two sets of apartments for my new home, with a total area of ​​190 m2. I spent a total amount of 500000 yuan for the new homes including decoration. The apartments are good quality, with all HH facilities. Children work outside, with stable income. We have participated in pension insurance for landless peasants. Our life is stable, and we are satisfied with land compensation.

9th October 2013 Zongxian Zhao  No.3 Group Beiguan Village

Land acquisition for the roads has been finished, and the compensation is distributed according to 130,000 yuan per capita averagely. Compensation of 150000 yuan was paid for house demolition, and there are 3 sets of apartments for my new home. I spent a total amount of more than 500000 yuan for the new homes including decoration. I am 68 years old this year, and participated in pension insurance for landless peasants. My son works outside, with stable income. Now we do not have living problems. There are relatively a lot of working opportunities around Zhangye City, and the production and living problem can be solved.

9th October 2013 Director Deng  Beiguan Village

There are 530 HHs in Beiguan Village, with 7 groups and 1824 persons. There are only three minorities. Income per capita of 2012 is 6,800 yuan, of which 30% is agricultural income, the rest are secondary and tertiary industry income. Now there are 500 Mu of land for Group 1, 2, and 6. House demolition compensation policy is: compensation is made according to the compensation price determined by Government. And the village committees build up houses under the guideline of government, and sell them to house demolished HHs at the cost price of 1600 yuan/ m2. The houses are distributed according to population structure of the family. When there is child who is more than 12 years old in the family, the family receives 2 sets of apartment. The house sizes are 80, 95, 100, and 104 m2 respectively. The houses are allocated last August on ballot with a fair allocation process. The resettlement community is Beiguan community, with 60 businesses for the affected people to restore revenues. Land compensation fees are all paid out to affected people, and the construction is progressing smoothly.

Photo 3: Beiguan Resettlement Community

22nd May 2013 Minghu Zhang  Governor of Town

Land acquisition for North Third Ring, Zhaowu Road, and North Gaotai Road is already completed, with a road compensation standard of 21000yuan/mu, and minimum compensation standard for non-road using is 50000 yuan/mu. Since the land compensation fees are distributed within the group averagely, we can all accept this compensation policy. The house is implemented according to the policy of Zhangye City. Up to now on the acquisitioned road, there are 52 HHs demolitions, mainly include: Nanhua Village, Baita Village and Liuquan Village. Resettlement houses’ policies are different in each village, and these policies are all consulted fully with the local villagers. The resettlement houses are under construction.

22nd May 2013 Secretary Yi Zhang Director Peixiang Wang

Land acquisition in the village progresses relatively smoothly. Land acquisition for roads is 21000yuan/mu. Because it is public welfare project, villagers can accept this standard. A compensation standard for non-road using land is higher, reaching 66000yuan/mu. For the land compensation fees, 5% is set aside for villagers’ groups, and the rest 95% is distributed averagely according to population of villagers’ groups. Land compensation distribution process is fair. More than 90% villagers are satisfied. The village has helped the venerable groups according to policy, and their house and basic living will be raised up. People in our village all work outside. Normally the wage for working outside is 100-120 yuan per day.

Compensation is given to those who need to be relocated. The cost price for resettlement community is 1800 yuan/m2, and the house price for resettled HHs is 1200-1300yuan/m2, which is lower than the cost price. Normally the HH receive 2 sets of apartment. The relatively poor HH can at least buy one apartment.

21st May 2013 Zhaoyang Jia  Zhangye Municipal Land and Resource Bureau

Xindun Town land and resource bureau, Xindun Government, the responsible persons of the villagers’ Groups and villager representatives signed the investigation results. Compensation fees are calculated by Xindun Town Land and Resource Bureau according to regulated standards, reported to Zhangye Municipal Land and Resource Bureau for verification, and considered as the proof of signature for the agreement. Road compensation standard is 21000 yuan/mu. House and ground attachment compensation standards executed compensation standards of Zhangye City (which accords with the ADB approved standards in RP). Xindun Town and Villages signed house and ground attachment compensation agreements. Each village develops individually according to urban plan, and builds up resettlement community to distribute to affect HHs. Land compensation fee is distributed based on villagers’ group and per capital, and this method has been used for a long time.

## 1.2    Interviews of Dingxi City

April 25, 2017 Dingxi demolition Office, Director Hongsheng He

We attach great importance to land acquisition and demolition work. Most of residents housing demolition work has been completed. Now only six HHs (including the Shehuo Association), can not reach an agreement, because they are asking for too high price. We are doing the negotiation work. Three of them have appealed to the Court. We plan to complete the housing demolition work in June this year.

Note: the bellowing interviews are before this monitoring and evaluation.

October 9, 2016 Dingxi demolition Office, Director Jianjun Wang, Director Hanlin Xiao

The land acquisition and demolition work has achieved great progress. The municipal government policies and documents are implemented. There are some families need a judicial solution, and we are doing coordination work. We are going to release the payments for those who has already signed the agreements. We also focused on public participation. Most of the problems are resolved. For illegal constructions, there are corresponding compensation policies in Dingxi City. The construction quality is divided into three categories, class I is 800 yuan / square meter, class II is 700 yuan / square meter, and Class III is 600 yuan / square meter, and shall be specifically evaluated by assessment companies. The payment for illegal constructions shall be directly included into the house compensation agreement.

October 9, 2016 Bolin Village, Secretary Long Zhang

The land acquisition and house demolition in Bolin village is progressing in an orderly manner, and there are no major conflicts. The income of the APs has increased.

March 26, 2016 Hanlin Xiao

42 persons are affected by this land acquisition and house demolition, mainly from Fengxiang Town, Housing Construction Bureau, and City Investment Company.

City Investment Company chaired business, providing logistical support. Main leaders of Fengxiang town are responsible for this work, and Housing Construction Bureau is responsible for the agreement signing. During the measurement and survey, multi-parties have signed and recognized the investigation results. HHs with property swap are expected to move in on June 30, 2016, whereas HHs with relocation still need to prepare some materials. The income of APs does not decline; usually they are working as migrant workers outside. In our work, we paid attention to the consultation with affected HHs and conducted investigation seriously. Sometimes we worked till 23:00. To finish so much demolition in such a short time, the work load is heavy. There is some affected HHs, who does not want to sign, to get more compensation. The method to solve this problem is mainly consultation work.

15 March 2015, Zhigeng He

Two illegal constructions were solved by relevant department and the construction is underway. The resettlement program for the second contract package batch is still waiting for approval of Urban Planning Board after discussion. The survey for the land acquisition and house demolition of the third contract package batch is not completed yet. It is expected to carry out the research in June 2015 and complete the RP update in October 2015.

15 March 2015, Li Su, Secretary of Bolin Village

Xihuan resettlement program has not been decided yet, therefore, the house demolition has not been carried out. People wanted to have an apartment and a bungalow. People are willing to go to Mojiaping resettlement site. 100 mu lands have been acquisitioned, and compensation was given in accordance with regulations. There are five “Five Guarantee Households” in this village and they receive subsidies according to the policy. There are 20 first Class “low income” households, with a subsidy standard of 250 yuan / person / month; 30 Second Class “low income” households, with a subsidy standard of 190 yuan / person / month; 60 Third Class “low income” households, with a subsidy standard of 190 yuan / person / month; II 30, 120-yuan subsidy standards / person-months. The main income source of the APs is construction, service industry and industrial parks. Income is not going to decrease after land acquisition.

18 September 2014 Yichao Chen

My house (illegal construction) was built in 2012, without procedures. Because many people built, so we also did this. There are 4 people in my family.

Photo 4: illegal construction (chicken farmland)

18 September 2014, Deshou Ma, Group 1 of Beilin Village

Our house needs to be demolished for transportation project. I did not know we need to resettle. The house area is 900 m2, and we support the project construction. We have pension, and my son and daughter in law are working outside, with stable income.

Photo 5: ADB expert interview

18 September 2014, Jijun Zhao

This is my temporary house, mainly for operation, and I handled with business license. The old people in my family live in our old house.

23 May 2014, Director He, Dingxi Urban Investment Ltd.

The construction for Xincheng Avenue and Bridge has been started. The land acquisition is basically completed, but some villagers’ new planted sapling after construction still need to be compensated and this is under negotiation. The house and land measurement for the second batch is completed and the update of RP is being prepared. Two contract packages on Jiaotong Road are not started yet.

23 May 2014, Qiang Pan, Director of Anding District Resentment department

Anding District issued " Dingxi City compensation scheme for house demolition of construction projects " and determined specific policies for the demolition, such as: compensation methods, the house monetary compensation, property rights exchange, relocation, etc. ADB resettlement housing projects are all using these methods, and the specific resettlement program is still under development.

23 May 2014, Li Su, Secretary of Berlin Village

Land acquisition of Xincheng Avenue is finished, without any problem. The land compensation fees are paid out, and the compensation is based on the land acquired area and government regulated standards. Land acquisition and compensation are going relatively smooth. After land acquisition, the main way to recover income is to work outside. And there is subsidy for low income HHs. Live is stable. The next step of house demolition will be difficult. There are relative plenty of local job opportunities, and the villager can find a job if they want to work.

5th September 2013 Director Zhao Anding District Land and resource bureau

Land acquisition compensation policies implement No.115 file of Provincial Government. The land acquisition price for Bolin Village in this project is 72 yuan/m2, and young crops are 3 yuan/m2. Our bureau is responsible for the land acquisition work.

5th September 2013 Director Pan Anding District Urban Construction Bureau

We conducted investigation for the ADB loan project. The evaluation work is responsible by Fangyuan Evaluation Company, and the evaluated results are the proof of compensation. The evaluation work is ongoing. Relocation methods are: (1) Property swap plus currency. (2) Currency compensation (3) Allocating housing placement.

5th September 2013 Hui Jing  Manager of Fangyuan Evaluation Company

Our company is doing the evaluation, and we only evaluate the houses. The evaluated results will be taken as the proof of compensation.

5th September 2013 Li Su  secretary of Bolin Village

Xincheng Avenue refers to Group No. 6, 7, 8, and 9 of our village. The land acquisition price is 75 yuan / m2, and young crop price is 3 yuan / m2. The land compensation fees should be all given to villagers’ groups. The village committee will not set any aside. 30% of the villagers use the money for production, 40% deposit it in bank, and 30% of the villagers use it for personal house building or consumption. Villagers know the compensation standards. Two meetings are held in the town for land acquisition, and the town organized us to participate the meeting and get to know the policies. There are people in the village who cultivate sheep and cattle, and also people who work outside, with a monthly wage of 4000yuan.

There is no house demolition for Xincheng Avenue, while there is house demolition in Jiaotong Road, and the resettlement place is Mengjiaping of our village. Now 40 HHs have already built up there, and can still build up more.

# Annex 2 Basic monitoring data

## 2.1    Basic monitoring data of Zhangye City

Annex 2.1.1 project land acquisition situation ( as of April 30, 2017 )

|  |  | Planned |  |  |  |  |  | Actual |  |  |  |  |  | Actual percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Serial | Name | State owned land | Rural land |  |  |  |  | State owned land | Rural land |  |  |  |  |  |  |
|  |  |  | Arable land | House plot | Unit | Subtotal | Total |  | Arable land | House plot | Unit | Subtotal | Total |  |  |
|  |  | Mu | Mu | Mu | Mu | Mu | Mu | Mu | Mu | Mu | Mu | Mu | Mu |  |  |
| CZ1 | Zhaowu Rd. | 0 | 224.33 | 0.48 | 0.10 | 224.91 | 224.91 | 0 | 224.3 | 0.48 | 0.1 | 224.9 | 224.91 | 100.00% |  |
| CZ2 | North Gaotai Rd. | 0 | 71.11 | 15.36 | 36.23 | 122.70 | 122.70 | 0 | 71.1 | 15.36 | 36.23 | 122.7 | 122.70 | 100.00% |  |
| CZ2 | Mingle Rd. | 0 | 157.33 | 0.00 | 8.23 | 165.56 | 165.56 | 0 | 148.33 | 0 | 8.23 | 156.6 | 156.56 | 94.56% |  |
| CZ3 | Aili Avenue (north third ring) | 0 | 223.94 | 9.12 | 21.33 | 254.39 | 254.39 | 0 | 223.9 | 9.12 | 21.33 | 254.4 | 254.39 | 100.00% |  |
| CZ3 | Juyan Rd. | 0 | 24.56 | 0.00 | 0.00 | 24.56 | 24.56 | 0 | 24.6 | 0 | 0 | 24.6 | 24.56 | 100.00% |  |
| CZ4 | Lindong West Street (West Minghai Rd.) | 0 | 45.06 | 4.32 | 0.10 | 49.48 | 49.48 | 0 | 45.1 | 4.32 | 0.1 | 49.5 | 49.48 | 100.00% |  |
| CZ4 | Lindong East Street(East Minghai Rd.) | 0 | 61.52 | 0.00 | 0.10 | 61.62 | 61.62 | 0 | 61.5 | 0 | 0.1 | 61.6 | 61.62 | 100.00% |  |
| CZ5 | North Sunan Rd. | 0 | 51.55 | 3.84 | 6.00 | 61.39 | 61.39 | 0 | 51.5543 | 3.84 | 6 | 61.4 | 61.39 | 100.00% |  |
| CZ5 | Baita Street (Wulan Rd.) | 0 | 90.14 | 3.84 | 0.10 | 94.08 | 94.08 | 0 | 90.14 | 3.84 | 0.1 | 94.1 | 94.08 | 100.00% |  |
| CZ6 | South Linze Rd. | 0 | 47.96 | 15.36 | 6.27 | 69.59 | 69.59 | 0 | 48.4 | 15.36 | 6.27 | 70.0 | 70.03 | 100.63% |  |
| CZ6 | East Yonggu Rd. | 0 | 39.30 | 10.08 | 0.50 | 49.88 | 49.88 | 0 | 39.3 | 0 | 0 | 39.3 | 39.30 | 78.79% |  |
| CZ7 | Nanhua Street (Liaoquan Rd.) | 0 | 83.13 | 4.80 | 0.00 | 87.93 | 87.93 | 0 | 83.13 | 4.80 | 0.00 | 87.9 | 87.93 | 100.00% |  |
| CZ7 | Yuguan Rd. (Huota Rd.) | 0 | 75.46 | 0.00 | 0.10 | 75.56 | 75.56 | 0 | 75.46 | 0.00 | 0.10 | 75.6 | 75.56 | 100.00% |  |
| CZ8 | South 3rd Ring | 0 | 166.59 | 43.20 | 0.10 | 209.89 | 209.89 | 0 | 0 | 0 | 0 | 0.0 | 0.00 | 0.00% | Cancelled |
| CZ9 | Wenchang Rd. (Xuefu Rd.) | 0 | 97.56 | 19.20 | 0.00 | 116.76 | 116.76 | 0 | 59.60 | 19.20 | 0.00 | 78.8 | 78.80 | 67.49% |  |
| CZ9 | Danma Street (Banqiao Rd.) | 0 | 56.45 | 19.20 | 0.10 | 75.75 | 75.75 | 0 | 56.45 | 19.2 | 0.1 | 75.7 | 75.75 | 100.00% |  |
| CZ10 | Wulan Rd. (North 2rd Ring) | 0 | 403.28 | 0.00 | 0.10 | 403.38 | 403.38 | 0 | 203.28 | 0 | 0 | 203.3 | 203.28 | 50.39% | Cancelled |
| CZ15 | Zhangye Water Supply Plant | 33.09 | 0.00 | 0.00 | 0.00 | 0.00 | 33.09 | 33.09 | 0 | 0 | 0 | 0.0 | 33.09 | 100.00% |  |
|  | Subtotal | 33.09 | 1919.26 | 148.80 | 79.36 | 2147.42 | 2180.51 | 33.09 | 1506.15 | 95.52 | 78.66 | 1680.33 | 1713.42 | 78.58% |  |

Annex 2.1.2 Land acquisition progress (as of April 30, 2017)

|  |  | Planned |  |  |  | Actual |  |  |  | Actual percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | HHs | Population | Current arable land | Arable land auditioned | HHs | Population | Current arable land | Arable land auditioned | Arable land | HH |
| Village | Group | HH | person | Mu | Mu | HH | person | Mu | Mu | % | % |
| Beiguan | 1 | 85 | 310 | 251 | 41.7 | 85 | 310 | 209.3 | 41.7 | 100% | 100% |
|  | 2 | 164 | 400 | 200 | 27.3 | 0 | 0 | 0 | 0 | 0% | 0% |
|  | 3 | 64 | 232 | 234 | 28.1 | 64 | 232 | 205.94 | 28.1 | 100% | 100% |
|  | 4 | 53 | 208 | 146 | 6.9 | 53 | 208 | 139.07 | 6.9 | 100% | 100% |
|  | 5 | 53 | 215 | 208 | 28.1 | 53 | 215 | 179.94 | 28.1 | 100% | 100% |
|  | 6 | 42 | 146 | 137 | 28.9 | 42 | 146 | 108.05 | 28.9 | 100% | 100% |
|  | 7 | 120 | 320 | 257 | 39.4 | 79 | 308 | 227.90 | 29.1 | 74% | 66% |
| Xiguan | 6 | 57 | 195 | 298 | 21.5 | 57 | 195 | 276.50 | 21.5 | 100% | 100% |
|  | 7 | 65 | 216 | 299 | 108.4 | 65 | 216 | 238.78 | 60.22 | 56% | 100% |
|  | 8 | 56 | 228 | 320 | 89.0 | 56 | 0 | 320 | 0 | 0% | 100% |
| Nanzha | 4 | 46 | 163 | 259 | 9.0 | 46 | 163 | 250 | 9 | 100% | 100% |
|  | 8 | 36 | 113 | 240 | 37.7 | 36 | 113 | 202.3 | 37.7 | 100% | 100% |
|  | 9 | 34 | 107 | 214 | 5.9 | 0 | 0 | 214 | 0 | 0% | 0% |
| Nanhua | 5 | 68 | 231 | 366 | 93.7 | 68 | 119 | 272.30 | 93.7 | 100% | 100% |
|  | 6 | 60 | 214 | 409 | 131.4 | 60 | 136 | 277.60 | 131.4 | 100% | 100% |
|  | 7 | 55 | 158 | 328 | 159.8 | 55 | 158 | 168.2 | 159.8 | 100% | 100% |
|  | 8 | 43 | 144 | 375 | 125.2 | 43 | 144 | 249.8 | 125.2 | 100% | 100% |
|  | 9 | 62 | 226 | 568 | 68.7 | 62 | 226 | 499.3 | 68.7 | 100% | 100% |
|  | 10 | 41 | 148 | 369 | 80.7 | 41 | 148 | 288.3 | 80.7 | 100% | 100% |
|  | 11 | 70 | 201 | 421 | 97.2 | 70 | 201 | 323.8 | 97.2 | 100% | 100% |
| Qingsong | 2 | 73 | 231 | 372 | 35.7 | 73 | 231 | 336.3 | 35.7 | 100% | 100% |
|  | 3 | 57 | 252 | 323 | 25.6 | 57 | 252 | 297.4 | 25.6 | 100% | 100% |
|  | 4 | 61 | 222 | 347 | 47.4 | 61 | 222 | 299.6 | 47.4 | 100% | 100% |
|  | 5 | 39 | 184 | 265 | 9.0 | 39 | 184 | 256 | 9 | 100% | 100% |
|  | 6 | 80 | 272 | 324 | 70.8 | 80 | 248 | 253.2 | 70.8 | 100% | 100% |
|  | 7 | 58 | 223 | 265 | 86.5 | 51 | 206 | 189 | 76 | 88% | 88% |
|  | 8 | 33 | 195 | 242 | 46.8 | 33 | 195 | 195.2 | 46.8 | 100% | 100% |
| Liuquan | 1 | 77 | 271 | 298 | 39.8 | 77 | 271 | 258.24 | 39.76 | 100% | 100% |
|  | 2 | 88 | 352 | 424 | 25.7 | 88 | 352 | 398.32 | 25.7 | 100% | 100% |
|  | 3 | 102 | 399 | 418 | 13.0 | 102 | 399 | 404.98 | 13.0 | 100% | 100% |
|  | 5 | 74 | 226 | 363 | 29.1 | 74 | 226 | 333.89 | 29.1 | 100% | 100% |
|  | 6 | 64 | 247 | 409 | 26.9 | 64 | 247 | 382.13 | 26.9 | 100% | 100% |
| Baita | 5 | 57 | 215 | 208 | 34.6 | 57 | 215 | 173.37 | 34.6 | 100% | 100% |
|  | 6 | 115 | 413 | 280 | 33.0 | 115 | 413 | 247.04 | 33.0 | 100% | 100% |
| Changerzha | 1 | 54 | 187 | 275 | 20.0 | 40 | 138 | 275 | 0 | 0% | 74% |
|  | 2 | 55 | 189 | 349 | 21.7 | 40 | 137 | 349 | 0 | 0% | 73% |
|  | 5 | 54 | 189 | 226 | 20.0 | 28 | 98 | 226 | 0 | 0% | 52% |
|  | 7 | 40 | 153 | 250 | 31.7 | 20 | 77 | 250 | 0 | 0% | 50% |
| Huaer | 3 | 52 | 134 | 278 | 18.3 | 43 | 110 | 278 | 0 | 0% | 83% |
|  | 5 | 39 | 119 | 177 | 21.7 | 25 | 76 | 177 | 0 | 0% | 64% |
| Bayi | 7 | 47 | 224 | 307 | 33.3 | 0 | 0 | 307 | 0 | 0% | 0% |
| Total |  | 2,593 | 9,072 | 12,299 | 1,919.2 | 2202 | 7535 | 10537.8 | 1561.2 | 81% | 84.9% |

Annex 2.1.3-1 House demolition progress (as of April 30, 2017)

|  |  | Planned |  |  | Actual |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Residential house |  |  | Residential house |  |  | Existing issues |
| Serial | Road | HHs | Population | Area | HHs | Population | Area | Please refer to the replies of the memorandum. |
|  |  | HH | Person | ㎡ | HH | Person | ㎡ |  |
| CZ1 | Zhaowu Rd. | 1 | 4 | 369 | 1 | 4 | 369 |  |
| CZ2 | North Gaotai Rd. | 32 | 123 | 15729 | 32 | 123 | 15,729 |  |
| CZ2 | Mingle Rd. | 0 | 0 | 0 | 0 | 0 | 0 |  |
| CZ3 | Aili Avenue (north third ring) | 19 | 73 | 9312 | 19 | 73 | 9,312 |  |
| CZ3 | Juyan Rd. | 0 | 0 | 0 | 0 | 0 | 0 |  |
| CZ4 | Lindong West Street (West Minghai Rd.) | 9 | 35 | 3443 | 1 | 4 | 120 |  |
| CZ4 | Lindong East Street (East Minghai Rd.) | 0 | 0 | 0 | 0 | 0 | 0 |  |
| CZ5 | North Sunan Rd. | 8 | 32 | 3885 | 8 | 32 | 3,885 |  |
| CZ5 | Baita Street (Wulan Rd.) | 8 | 32 | 3893 | 6 | 24 | 3,200 |  |
| CZ6 | South Linze Rd. | 32 | 124 | 15745 | 27 | 105 | 14,284 |  |
| CZ6 | East Yonggu Rd. | 21 | 80 | 10273 | 21 | 80 | 10,273 |  |
| CZ7 | Nanhua Street (Liaoquan Rd.) | 10 | 40 | 4857 | 0 | 0 | 0 |  |
| CZ7 | Yuguan Rd. (Huota Rd.) | 0 | 0 | 0 | 0 | 0 | 0 |  |
| CZ8 | South 3rd Ring | 90 | 338 | 32855 | 0 | 0 | 0 |  |
| CZ9 | Wenchang Rd. (Xuefu Rd.) | 42 | 161 | 19729 | 30 | 121 | 14,092.143 |  |
| CZ9 | Danma Street (Banqiao Rd.) | 40 | 152 | 20249 | 40 | 152 | 20,249 |  |
| CZ10 | Wulan Rd. (North 2rd Ring) | 0 | 0 | 0 | 0 | 0 | 0 |  |
| CZ15 | Zhangye Water Supply Plant | 0 | 0 | 0 | 0 | 0 | 0 |  |
|  | Total | 312 | 1,194 | 140,339 | 185 | 718 | 91,513.143 |  |

Annex 2.1.3-2 House demolition progress (as of April 30, 2017)

|  |  | Planned |  |  | Actual |  |  | Percentage |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Village | Group | HHs | Population | Area | HHs | Population | Area | HHs | Area |  |
|  |  | HH | Person | m2 | HH | Person | m2 | % | % |  |
| Beiguan | 1 | 10 | 40 | 4897 | 0 | 0 | 0 | 0% | 0% |  |
|  | 2 | 2 | 8 | 600 | 0 | 0 | 0 | 0% | 0% |  |
|  | 3 | 30 | 117 | 14103 | 30 | 117 | 14103 | 100% | 100% |  |
|  | 4 | 12 | 47 | 6320 | 12 | 47 | 6320 | 100% | 100% |  |
|  | 5 | 12 | 47 | 6014 | 12 | 47 | 6014 | 100% | 100% |  |
|  | 6 | 16 | 62 | 7885 | 16 | 62 | 7885 | 100% | 100% |  |
| Nanzha | 4 | 7 | 27 | 3528 | 7 | 27 | 3528 | 100% | 100% |  |
|  | 8 | 25 | 98 | 12363 | 25 | 98 | 12363 | 100% | 100% |  |
| Nanhua | 6 | 8 | 32 | 3885 | 8 | 32 | 3885 | 100% | 100% |  |
|  | 8 | 9 | 35 | 3443 | 9 | 35 | 3443 | 100% | 100% |  |
|  | 9 | 40 | 156 | 19597 | 32 | 116 | 16761 | 80% | 86% |  |
|  | 10 | 1 | 4 | 376 | 1 | 4 | 376 | 100% | 100% |  |
| Qingsong | 2 | 10 | 39 | 4857 | 0 | 0 | 0 | 0% | 0% |  |
|  | 3 | 21 | 82 | 9895 | 14 | 58 | 7114 | 67% | 72% |  |
| Liuquan | 1 | 2 | 8 | 1383 | 2 | 8 | 1383 | 100% | 100% |  |
| Baita | 5 | 12 | 47 | 5824 | 12 | 47 | 5824 | 100% | 100% |  |
|  | 6 | 5 | 20 | 2514 | 5 | 20 | 2514 | 100% | 100% |  |
| Changerzha | 1 | 24 | 74 | 8969 | 0 | 0 | 0 | 0% | 0% | cancelled |
|  | 2 | 22 | 79 | 7969 | 0 | 0 | 0 | 0% | 0% | cancelled |
|  | 5 | 22 | 85 | 7993 | 0 | 0 | 0 | 0% | 0% | cancelled |
| Huaer | 5 | 10 | 42 | 3667 | 0 | 0 | 0 | 0% | 0% | cancelled |
| Bayi | 7 | 12 | 45 | 4257 | 0 | 0 | 0 | 0% | 0% | cancelled |
| Total |  | 312 | 1,194 | 140,339 | 185 | 718 | 91513 | 59% | 65% |  |

Annex 2.1.3-3 House demolition progress (as of April 30, 2017)

|  | Planned |  |  | Actual |  |  | Actual percentage |  | Resettlement | Resettlement place |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | HHs | Population | Area | HHs | Population | Area | HHs | Area |  |  |
|  | 82 | 321 | 39819 | 70 | 273 | 34322 | 85% | 86% |  |  |
| Nanzha | 32 | 125 | 15891 | 32 | 125 | 15891 | 100% | 100% |  |  |
| Nanhua | 58 | 226 | 27301 | 50 | 187 | 24465 | 86% | 90% |  |  |
| Qingsong | 31 | 121 | 14752 | 14 | 58 | 7114 | 45% | 48% |  |  |
| Liuquan | 2 | 8 | 1383 | 2 | 8 | 1383 | 100% | 100% |  |  |
| Baita | 17 | 67 | 8338 | 17 | 67 | 8338 | 100% | 100% |  |  |
| chengerzha | 68 | 238 | 24931.2 | 0 | 0 | 0 | 0% | 0% |  |  |
| Huaer | 10 | 43 | 3667 | 0 | 0 | 0 | 0% | 0% |  |  |
| Bayi | 12 | 45 | 4257 | 0 | 0 | 0 | 0% | 0% |  |  |
| Subtotal | 312 | 1,194 | 140,339 | 185 | 718 | 91513 | 59% | 65% |  |  |

Annex 2.1.4 Progress of affected self-employed HH (as of April 30, 2017)

|  |  |  | Planned |  |  |  |  |  |  |  | Actual |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Road | Unit name | Unit nature | Occupation Area | House area | Formal worker | Temporary worker | Subtotal | Operation situation | Annual revenue | Salary situation | House area | Formal worker | Temporary worker | Subtotal | Operation situation | Annual revenue | Salary situation |
|  |  | M2 | M2 | M2 | Person | Person | Person |  | Yuan | Yuan/month |  | Person | Person | Person |  | Yuan | Yuan/month |
| Aili Avenue(north third ring) | Small shop | private | 36 | 30 | 1 |  | 1 | Run normally | 16000 | 700 | 30 | 1 |  | 1 | Run normally | 26000 | 1300 |
| Wulan Rd. (North 2rd Ring) | Small shop | private | 25 | 20 | 1 |  | 1 | Run normally | 18000 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Restaurant | private | 46 | 40 | 1 | 2 | 3 | Run normally | 40000 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Store | private | 38 | 33 | 1 |  | 1 | Run normally | 20000 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Paper Mill | State owned | 11559 | 1334 | 10 | 4 | 14 | Stop production |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Chemical factory | State owned | 2668 | 5780 | 10 | 13 | 23 | Stop production |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Juyan Rd. | Small shop | private | 36 | 34 | 1 |  | 1 | Run normally | 15000 | 600 | 34 | 1 |  | 1 | Run normally | 25000 | 1300 |
| South third ring | Tobacco shops | private | 32 | 30 | 1 |  | 1 | Run normally | 16000 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| North Gaotai Rd. | Small shop | private | 40 | 36 | 1 |  | 1 | Run normally | 18000 | 700 | 36 | 1 | 0 | 1 | 0 | 0 | 0 |
|  | Flour mills | private | 685 | 680 | 1 |  | 1 | Run normally | 50000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Nanhua Village committee |  | 870 | 860 | 1 | 2 | 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Village clinics |  | 62 | 60 | 1 | 1 | 2 | Run normally | 30000 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| East Yongu Rd. | Small shop | private | 35 | 32 | 1 |  | 1 | Run normally | 16000 | 700 | 32 | 1 | 0 | 1 | 0 | 0 | 0 |
| Mingle Rd. | Shop | private | 40 | 38 | 1 |  | 1 | Run normally | 14000 | 600 | 38 | 1 |  | 1 | Run normally | 24000 | 1300 |
| Wenchang Rd.(xuefu Rd.) | Small shop | private | 38 | 35 | 1 |  | 1 | Run normally | 12000 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Store | private | 36 | 34 | 1 |  | 1 | Run normally | 17000 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Barbers | private | 34 | 33 | 1 |  | 1 | Run normally | 36000 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | supermarket | private | 85 | 82 | 1 | 1 | 2 | Run normally | 68000 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Beiguan village committee |  | 266 | 360 | 3 | 2 | 5 |  |  |  |  |  |  |  |  |  |  |
| Nanhua Street (Liaoquan Rd.) | Salesroom | private | 38 | 35 | 1 |  | 1 | Run normally | 13000 | 500 | 35 | 1 | 0 | 1 | 0 | 0 | 0 |
| West Linsong Street (West Minghai Rd.) | Small shop | private | 30 | 26 | 1 |  | 1 | Run normally | 13000 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Danma Street (Banqiao Rd.) | Small shop | private | 32 | 30 | 1 |  | 1 | Run normally | 14000 | 600 | 30 | 1 |  | 1 | Run normally | 25000 | 1500 |
| Wulan Rd. (North 2rd Ring) | Salesroom | private | 40 | 38 | 1 |  | 1 | Run normally | 12000 | 400 | 38 | 1 | 0 | 1 | 0 | 0 | 0 |
| Total |  |  | 16,771 | 9,680 | 43 | 25 | 68 | 0 |  |  | 273 | 8 | 0 | 8 |  |  |  |

Annex 2.1.5 House compensation standard

|  |  |  | Panned | Actual |
| --- | --- | --- | --- | --- |
| Serial | Project | Unit | Price (yuan) | Price (yuan) |
| 1 | Brick concrete house | m2 | 800 | 928 |
| 2 | Brick concrete bungalow | m2 | 500 | 580 |
| 3 | Brick wood | m2 | 350 | 406 |
| 4 | Brick earth wood | m2 | 300 | 348 |
| 5 | Earth wood | m2 | 220 | 255.2 |
| 6 | Bulk water | m2 | 50 | 58 |
| 7 | Brick wall | m2 | 200 | 232 |
| 8 | Earth wall | m2 | 80 | 92.8 |
| 9 | Brick floor | m2 | 30 | 34.8 |
| 10 | Concrete floor | m2 | 50 | 58 |
| 11 | Asphalt pavement | m2 | 30 | 34.8 |
| 12 | Standard shed | m2 | 80 | 92.8 |
| 13 | Temporary shed | m2 | 50 | 58 |
| 14 | Brick toilet | set | 200 | 232 |
| 15 | Earth toilet | set | 100 | 116 |
| 16 | Septic tanks | set | 1500 | 1740 |
| 17 | Water wells | set | 150 | 174 |
| 18 | Seepage wells | set | 150 | 174 |
| 19 | Press Wells | set | 150 | 174 |
| 20 | Telephone | set | 50 | 58 |
| 21 | close-up (TV) | HH | 350 | 406 |
| 22 | Rain Shed | Set | 300 | 348 |
| 23 | Brick vegetable cellar | Set | 300 | 348 |
| 24 | Earth vegetable cellar | Set | 200 | 232 |
| 25 | Tombs | Set | 800 | 928 |
| 26 | U-shape channel | m | 50 | 58 |
| 27 | Fences | m | 10 | 11.6 |
| 28 | Soil Papaya Room | Set | 500 | 580 |
| 29 | Brick concrete well house | m2 | 400 | 464 |
| 30 | Motor-pumped well | Set | 60000-80000 | 69600-92800 |
| 31 | Large-diameter wells | Set | 5000 | 5800 |
| 32 | Water Tank | Set | 300 | 348 |
| 33 | Culvert | m | 30 | 34.8 |
| 34 | Low pressure pipe | m | 30 | 34.8 |
| 35 | Observation wells | Set | 150 | 174 |
| 36 | Out the hydrant | Set | 150 | 174 |
| 37 | Water pipe | m | 15 | 17.4 |
| 38 | Sluice | Set | 100 | 116 |
| 39 | Small bridge | Set | 100 | 116 |
| 40 | Electricity Poles | Set | 150 | 174 |
| 41 | Electricity Distribution box | Set | 200 | 232 |
| 42 | Embedding cord | m | 15 | 17.4 |
| 43 | Power cord | m | 50 | 58 |
| 44 | Power Package | Set | 1000 | 1160 |
| 45 | Meter box | Set | 200 | 232 |
| 46 | Billboard | Set | 100 | 116 |
| 47 | Wrought iron fence | Set | 100 | 116 |
| 48 | Iron gates | Set | 160 | 185.6 |
| 49 | Cement pillar | Unit | 20 | 23.2 |
| 50 | Defending Fence | m | 100 | 116 |
| 51 | Tank | Set | 400 | 464 |
| 52 | Solar | Set | 500 | 580 |
| 53 | Metal housing | m2 | 300 | 348 |
| 54 | Transition fee | HH/month | 200 | 232 |
| 54 | Moving fee | HH | 200 | 232 |
| 55 | Reword fee | HH | 3000 | 3480 |

Annex 2.1.6 Ground attachment compensation standard

| Category of trees | Unit | Planned | Actual |
| --- | --- | --- | --- |
| Sapling | Yuan/unit | 1.5 | 1.74 |
| Small trees | Yuan/unit | 5 | 5.8 |
| Auxiliary materials | Yuan/unit | 14 | 16.24 |
| Timber purlins | Yuan/unit | 20 | 23.2 |
| Timber beams | Yuan/unit | 100 | 116 |
| Fruit trees with fruits | Yuan/unit | 200 | 232 |
| Fruit trees without fruits | Yuan/unit | 50 | 58 |
| Saplings of fruit trees | Yuan/unit | 5 | 5.8 |
| Grape | Yuan/unit | 100 | 116 |
| Landscape trees | Yuan/unit | 60 | 69.6 |
| Young crops | Yuan/mu | 800 | 928 |
| Alfalfa | Yuan/mu | 1000 | 1160 |
| Chives | Yuan/mu | 1200 | 1392 |
| Exposed chives | Yuan/mu | 8000 | 9280 |
| Greenhouse chives | Yuan/mu | 16000 | 18560 |
| Efficient greenhouses | Yuan /m2 | 37.5 | 43.5 |
| 2nd greenhouses | Yuan /m2 | 24 | 27.84 |

Annex 2.1.7 Land acquisition of sample HHs of Zhangye City

| Serial | Town | Village | Group | Name | Population | Income |  |  | Before land acquisition |  |  |  | Land acquisition |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Agriculture | Working outside | Subtotal | Arable land | Dry land | Garden | Subtotal | Arable land | Dry land | Garden | Subtotal | Compensation | Received date |
|  |  |  |  |  |  | Yuan | Yuan | Yuan | Mu | Mu | Mu | Mu | Mu | Mu | Mu | Mu | Yuan | Yuan |
|  | Xindun | Beiguan | 3 | Zongsong Zhao | 4 | 0 | 50000 | 50000 | 4.8 |  |  | 4.8 | 4.8 |  |  | 4.8 | 520000 | 20130630 |
|  |  |  |  | Zongxiain Zhao | 6 | 0 | 70000 | 70000 | 6.4 |  |  | 6.4 | 6.4 |  |  | 6.4 | 780000 | 20130630 |
|  |  |  |  | Dengguo Zhao | 4 | 0 | 80000 | 80000 | 5.1 |  |  | 5.1 | 5.1 |  |  | 5.1 | 520000 | 20130630 |
|  |  |  |  | Zongqing Zhao | 7 | 0 | 120000 | 120000 | 3.6 |  |  | 3.6 | 3.6 |  |  | 3.6 | 910000 | 20130630 |
|  |  |  |  | Rong Qi | 6 | 0 | 180000 | 180000 | 4.8 |  |  | 4.8 | 4.8 |  |  | 4.8 | 780000 | 20130630 |
|  |  |  |  | Yuguo Zhao | 5 | 0 | 40000 | 40000 | 6.5 |  |  | 6.5 | 6.5 |  |  | 6.5 | 780000 | 20130630 |
|  |  |  |  | Wenguo Zhao | 3 | 0 | 80000 | 80000 | 3.6 |  |  | 3.6 | 3.6 |  |  | 3.6 | 390000 | 20130630 |
|  |  |  |  | Xinghong Zhang | 6 | 0 | 250000 | 250000 | 3.9 |  |  | 3.9 | 3.9 |  |  | 3.9 | 780000 | 20130630 |
|  |  |  | 7 | Wangui Ren | 4 | 0 | 150000 | 150000 | 2.7 |  |  | 2.7 | 2.7 |  |  | 2.7 | 624000 | 20130630 |
|  |  |  |  | Xingfu Shao | 6 | 0 | 160000 | 160000 | 6 |  |  | 6 | 6 |  |  | 6 | 1092000 | 20130630 |
|  |  |  |  | Xuelong Shao | 7 | 0 | 210000 | 210000 | 4.5 |  |  | 4.5 | 4.5 |  |  | 4.5 | 1092000 | 20130630 |
|  |  |  |  | Wanyi Ren | 3 | 0 | 150000 | 150000 | 4 |  |  | 4 | 4 |  |  | 4 | 468000 | 20130630 |
|  |  |  |  | Bin Ren | 5 | 0 | 150000 | 150000 | 2.8 |  |  | 2.8 | 2.8 |  |  | 2.8 | 780000 | 20130630 |
|  |  |  |  | Hu Shao | 4 | 0 | 120000 | 120000 | 4.4 |  |  | 4.4 | 4.4 |  |  | 4.4 | 624000 | 20130630 |
|  |  |  |  | Xueshun Shao | 6 | 0 | 120000 | 120000 | 3.7 |  |  | 3.7 | 3.7 |  |  | 3.7 | 936000 | 20130630 |
|  |  | Subtotal |  |  | 76 | 0 | 1930000 | 1930000 | 66.8 |  |  | 66.8 | 66.8 |  |  | 66.8 | 11076000 | 301,959,450 |
|  |  | Qingsong | 2 | Jin Ye | 5 | 0 | 45000 | 45000 | 6 |  |  | 6 | 6 |  |  | 6 | 900000 |  |
|  |  |  |  | Zhongguo Zhao | 5 | 0 | 56000 | 56000 | 6 |  |  | 6 | 6 |  |  | 6 | 900000 |  |
|  |  |  |  | Ping Ye | 4 | 0 | 44000 | 44000 | 6 |  |  | 6 | 6 |  |  | 6 | 720000 |  |
|  |  |  |  | Peng Ye | 4 | 0 | 55000 | 55000 | 6 |  |  | 6 | 6 |  |  | 6 | 720000 |  |
|  |  |  |  | Hai Ye | 3 | 0 | 30000 | 30000 | 4.5 |  |  | 4.5 | 4.5 |  |  | 4.5 | 540000 |  |
|  |  |  | 3 | Xin Wang | 4 | 0 | 33000 | 33000 | 5 |  |  | 5 | 5 |  |  | 5 | 560000 |  |
|  |  |  |  | Xingjian Zhao | 4 | 0 | 40000 | 40000 | 5 |  |  | 5 | 5 |  |  | 5 | 560000 |  |
|  |  |  |  | Jianbin Wang | 5 | 0 | 65000 | 65000 | 6.25 |  |  | 6.25 | 6.25 |  |  | 6.25 | 700000 |  |
|  |  |  |  | Yuan Han | 2 | 0 | 1080 | 1080 | 2.5 |  |  | 2.5 | 2.5 |  |  | 2.5 | 280000 |  |
|  |  |  |  | Jiancheng Li | 3 | 0 | 45000 | 45000 | 3.75 |  |  | 3.75 | 3.75 |  |  | 3.75 | 420000 |  |
|  |  |  | 4 | Jianjun Dai | 3 | 0 | 33000 | 33000 | 4.8 |  |  | 4.8 | 4.8 |  |  | 4.8 | 420000 |  |
|  |  |  |  | Jianguo Li | 6 | 0 | 40000 | 40000 | 8 |  |  | 8 | 8 |  |  | 8 | 840000 |  |
|  |  |  |  | Qiangguo Zhao | 5 | 0 | 45000 | 45000 | 6 |  |  | 6 | 6 |  |  | 6 | 700000 |  |
|  |  |  |  | Xinghong Zhang | 3 | 0 | 35000 | 35000 | 6.8 |  |  | 6.8 | 6.8 |  |  | 6.8 | 420000 |  |
|  |  |  |  | Xingjun Zhang | 3 | 0 | 20000 | 20000 | 6 |  |  | 6 | 6 |  |  | 6 | 420000 |  |
|  |  | Subtotal |  |  | 59 | 0 | 587080 | 587080 | 82.6 |  |  | 82.6 | 82.6 |  |  | 82.6 | 9,100,000 |  |
|  |  | Nanhua | 5 | Dexi Wang | 1 | 0 | 10000 | 10000 | 2 |  |  | 2 | 2 |  |  | 2 | 60000 |  |
|  |  |  |  | Wanchang Chen | 3 | 0 | 21000 | 21000 | 5 |  |  | 5 | 5 |  |  | 5 | 180000 |  |
|  |  |  | 8 | Jirui Zhao | 4 | 0 | 60000 | 60000 | 13 |  |  | 13 | 13 |  |  | 13 | 20000 |  |
|  |  |  |  | Xingbiao Lei | 1 | 0 | 10000 | 10000 | 6 |  |  | 6 | 6 |  |  | 6 | 5000 |  |
|  |  |  |  | Cailin Zhao | 3 | 0 | 40000 | 40000 | 8.5 |  |  | 8.5 | 8.5 |  |  | 8.5 | 15000 |  |
|  |  |  |  | Yiquan Wang | 3 | 0 | 48000 | 48000 | 15 |  |  | 15 | 15 |  |  | 15 | 15000 |  |
|  |  |  |  | Yingcheng Gao | 7 | 0 | 110000 | 110000 | 11 |  |  | 11 | 11 |  |  | 11 | 35000 |  |
|  |  |  | 6 | Jicai Lian | 4 | 0 | 48000 | 48000 | 9.68 |  |  | 9.68 | 9.68 |  |  | 9.68 | 260000 |  |
|  |  |  |  | Zhenghua Lian | 4 | 0 | 40000 | 40000 | 5.4 |  |  | 5.4 | 5.4 |  |  | 5.4 | 260000 |  |
|  |  |  |  | Zhibin Rong | 4 | 0 | 50000 | 50000 | 7.6 |  |  | 7.6 | 7.6 |  |  | 7.6 | 260000 |  |
|  |  |  |  | Xiaohong Rong | 7 | 0 | 90000 | 90000 | 12 |  |  | 12 | 12 |  |  | 12 | 455000 |  |
|  |  |  |  | Jiyin Zhang | 4 | 0 | 56000 | 56000 | 9.6 |  |  | 9.6 | 9.6 |  |  | 9.6 | 260000 |  |
|  |  |  |  | Fubin Wei | 3 | 0 | 12000 | 12000 | 3 |  |  | 3 | 3 |  |  | 3 | 195000 |  |
|  |  |  |  | Fucai Wei | 5 | 0 | 50000 | 50000 | 14 |  |  | 14 | 14 |  |  | 14 | 325000 |  |
|  |  |  |  | Qianzhi Pu | 3 | 0 | 45000 | 45000 | 5.57 |  |  | 5.57 | 5.57 |  |  | 5.57 | 195000 |  |
|  |  |  |  | Aijun Pu | 5 | 0 | 50000 | 50000 | 6.35 |  |  | 6.35 | 6.35 |  |  | 6.35 | 325000 |  |
|  |  |  |  | Zihong Wang | 4 | 0 | 50000 | 50000 | 11.4 |  |  | 11.4 | 11.4 |  |  | 11.4 | 260000 |  |
|  |  |  | 5 | Xinghong Chen | 4 | 0 | 48000 | 48000 | 1 |  |  | 1 | 1 |  |  | 1 | 240000 |  |
|  |  |  | 7 | Yi Zhang | 3 | 0 | 45000 | 45000 |  |  |  | 0 |  |  |  | 0 | 300000 |  |
|  |  |  | 1 | Peixiang Wang | 5 | 0 | 40000 | 40000 | 10 |  |  | 10 | 10 |  |  | 10 | 440000 |  |
|  |  | Subtotal |  |  | 77 | 0 | 923000 | 923000 | 156.1 |  |  | 156.1 | 156.1 |  |  | 156.1 | 4,105,000 |  |
|  |  | Total |  |  | 212 | 0 | 3,440,080 | 3,440,080 | 305.5 |  |  | 305.5 | 305.5 |  |  | 305.5 | 24,281,000 | 301,959,450 |

Annex 2.1.8 Property of Sample HHs of Zhangye City

| Serial | Town | Village | Group | House | House area | Colored TV | Refrigerator | Wash machine | Tractor | Motorcycle | Pump | Big living stock | Internet | Telephone | Car |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Rooms | M2 | Set | Set | Set | Set | Set | Set | Unit | Set | Set | Set |
| Xindun | Beiguan | 3 | Zongsong Zhao | 15 | 349 | 1 | 1 | 1 |  | 1 |  |  | 1 | 3 | 0 |
|  |  |  | Zongxian Zhao | 12 | 180 | 2 | 2 | 1 |  | 1 |  |  | 1 | 2 | 0 |
|  |  |  | Dengguo Zhao | 18 | 267 | 1 | 1 | 1 |  | 2 |  |  | 1 | 3 | 0 |
|  |  |  | Zongbo Zhao | 12 | 315 | 1 | 1 | 1 |  | 2 |  |  | 1 | 1 | 0 |
|  |  |  | Zongqin Zhao | 21 | 376 | 2 | 2 | 2 |  | 2 |  |  | 1 | 3 | 1 |
|  |  |  | Rong Qi | 20 | 290 | 2 | 1 | 2 |  | 2 |  |  | 1 | 3 | 1 |
|  |  |  | Yiquan Zhao | 3 | 78 | 2 | 2 | 2 |  | 2 |  |  | 1 | 4 | 2 |
|  |  |  | Wenguo Zhao | 28 | 256 | 1 | 1 | 1 |  | 1 |  |  | 1 | 3 | 1 |
|  |  |  | Xinghou zhao | 12 | 270 | 2 | 2 | 2 |  | 2 |  |  | 1 | 4 | 3 |
|  |  | 7 | Wangui ren | 18 | 297 | 1 | 1 | 1 |  | 1 |  |  | 1 | 3 | 0 |
|  |  |  | Xingfu shao | 26 | 599 | 2 | 2 | 2 |  | 2 |  |  | 1 | 4 | 2 |
|  |  |  | Xuelong shao | 28 | 658 | 2 | 2 | 2 |  | 2 |  |  | 1 | 4 | 2 |
|  |  |  | Wanyi ren | 22 | 336 | 1 | 1 | 1 |  | 1 |  |  | 1 | 2 | 1 |
|  |  |  | Bin ren | 16 | 229 | 1 | 1 | 1 |  | 1 |  |  | 1 | 3 | 1 |
|  |  |  | Hu shao | 3 | 89.5 | 1 | 1 | 1 |  | 1 |  |  | 1 | 2 | 1 |
|  |  |  | Xueshun shao | 16 | 345 | 2 | 2 | 2 |  | 1 |  |  | 1 | 4 | 1 |
|  | Subtotal |  |  | 270 | 4934.5 | 24 | 23 | 23 | 0 | 24 | 0 | 0 | 16 | 48 | 16 |
|  | Qingsong | 2 | Qin ye | 5 | 70 | 1 | 1 | 1 |  | 1 |  |  | 1 | 3 | 1 |
|  |  |  | Zhongguo zhao | 5 | 70 | 1 | 1 | 1 |  | 1 |  |  | 1 | 3 | 1 |
|  |  |  | Ping ye | 4 | 60 | 1 | 1 | 1 |  | 1 |  |  | 1 | 2 | 1 |
|  |  |  | Peng ye | 4 | 60 | 1 | 1 | 1 |  | 1 |  |  | 1 | 2 | 0 |
|  |  |  | Hai ye | 2 | 30 | 1 |  | 1 |  | 1 |  |  | 1 | 1 | 0 |
|  |  | 3 | Xin wang | 4 | 65 | 1 |  | 1 |  | 1 |  |  | 1 | 2 | 0 |
|  |  |  | Xingjian zhao | 3 | 55 | 1 | 1 | 1 |  | 1 |  |  | 1 | 2 | 0 |
|  |  |  | Jianbin wang | 5 | 70 | 1 | 1 | 1 |  | 1 |  |  | 1 | 3 | 1 |
|  |  |  | Yuan Han | 2 | 30 | 1 |  | 1 |  |  |  |  | 1 | 1 | 0 |
|  |  |  | Jiancheng li | 4 | 60 | 1 | 1 | 1 |  | 1 |  |  | 1 | 2 | 0 |
|  |  | 4 | Jianjun dai | 3 | 75 | 1 |  | 1 |  |  |  |  | 1 | 3 | 1 |
|  |  |  | Jianguo li | 4 | 80 | 2 |  | 1 |  | 2 |  |  | 1 | 4 | 1 |
|  |  |  | Qiangguo zhao | 3 | 70 | 1 |  | 1 |  | 1 |  |  | 1 | 3 | 0 |
|  |  |  | Xinghong zhang | 3 | 60 | 1 |  | 1 |  | 1 |  |  | 1 | 3 | 0 |
|  |  |  | Xingjun zhang | 2 | 40 | 1 | 1 | 1 |  | 1 |  |  | 1 | 2 | 0 |
|  | Subtotal |  |  | 53 | 895 | 16 | 8 | 15 | 0 | 14 | 0 | 0 | 15 | 36 | 6 |
|  | Nanhua | 5 | Dexi wang | 5 | 60 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |
|  |  |  | Wanchang chen | 10 | 100 | 1 |  | 1 |  |  |  | 1 | 1 | 1 | 0 |
|  |  | 8 | Jirui zhao | 15 | 180 | 1 | 1 | 1 |  | 1 |  |  | 1 | 3 | 1 |
|  |  |  | Xingbiao lei | 3 | 45 | 1 |  |  |  |  |  |  | 1 | 1 | 0 |
|  |  |  | Cailin zhao | 5 | 75 | 1 |  | 1 |  | 1 |  |  | 1 | 2 | 1 |
|  |  |  | Yiquan wang | 8 | 96 | 1 | 1 | 1 |  | 1 |  |  | 1 | 2 | 1 |
|  |  |  | Yingcheng gao | 13 | 165 | 1 | 1 | 1 |  | 1 |  |  | 1 | 5 | 1 |
|  |  | 6 | Jicai lian | 10 | 120 | 1 | 1 | 1 |  | 2 |  |  | 1 | 3 | 1 |
|  |  |  | Zhenghua lian | 10 | 120 | 1 | 1 | 1 |  | 2 |  |  | 1 | 2 | 0 |
|  |  |  | Zhibin rong | 8 | 96 | 1 | 1 | 1 |  | 1 |  |  | 1 | 3 | 0 |
|  |  |  | Xiaohong rong | 10 | 120 | 1 | 1 | 1 |  | 1 |  |  | 1 | 2 | 1 |
|  |  |  | Jiyin zhang | 12 | 144 | 1 | 1 | 1 |  | 2 |  |  | 1 | 2 | 0 |
|  |  |  | Fubin wei | 6 | 72 | 1 |  | 1 |  | 1 |  |  | 1 | 1 | 0 |
|  |  |  | Fucai wei | 15 | 180 | 1 | 1 | 1 |  | 2 |  |  | 1 | 4 | 0 |
|  |  |  | Qianzhi pu | 6 | 72 | 1 | 1 | 1 |  | 3 |  |  | 1 | 3 | 1 |
|  |  |  | Caijun pu | 8 | 96 | 1 | 1 | 1 |  | 2 |  |  | 1 | 1 | 1 |
|  |  |  | Zihong wang | 10 | 120 | 1 | 1 | 1 |  | 3 |  |  | 1 | 2 | 1 |
|  |  | 5 | Xinghong chen | 11 | 130 | 1 | 1 | 1 |  | 1 |  |  | 1 | 2 | 1 |
|  |  | 7 | Yi zhang | 12 | 140 | 1 | 1 | 1 |  | 1 |  |  | 1 | 2 | 1 |
|  |  | 1 | Peixiang wang | 12 | 140 | 1 | 1 | 1 |  | 1 |  |  | 1 | 2 | 0 |
|  | Subtotal |  |  | 189 | 2271 | 20 | 15 | 18 | 0 | 26 | 0 | 1 | 20 | 44 | 11 |
|  | Total |  |  | 512 | 8100.5 | 60 | 46 | 56 | 0 | 64 | 0 | 1 | 51 | 128 | 33 |

Annex 2.1.9 Sample Survey of housing compensation (April 2017)

| Village |  | House compensation | Floating up 20% | Basic reword | Time limit reward | Brothers living together | Subtotal | Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Yuan | Yuan | Yuan | Yuan | Yuan | Yuan |  |
| Group 2 of Qingsong Village | Jing Ye | 177720 | 35544 | 30000 | 30000 | 0 | 273264 | April 20,2017 |
| Group 2 of Qingsong Village | Ping Ye | 90547.5 | 17109.5 | 15000 | 15000 | 10000 | 147657 | April 13,2017 |
| Group 2 of Qingsong Village | Xingbin Zhang | 145789 | 29158 | 30000 | 30000 | 0 | 234947 | April 12,2017 |
| Group 2 of Qingsong Village | Wenqiang Ye | 150451 | 30090 | 30000 | 30000 | 20000 | 260541 | April 12,2017 |
| Group 2 of Qingsong Village | Long Ye | 77748 | 16550 | 15000 | 15000 | 10000 | 134298 | April 12,2017 |

2.2    monitoring data of Dingxi city

Annex 2.2.1 Land acquisition of sample HHs of Dingxi City

| Serial | Town | Village | Group | Name | Population | Income |  |  | Before land acquisition |  |  |  | Before land acquisition |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Agriculture | Working outside | Subtotal | Arable land | Dry land | Garden | Subtotal | Arable land | Dry land | Garden | Subtotal | Compensation | Received date | Note |
|  |  |  |  |  |  | Yuan | Yuan | Yuan | Mu | Mu | Mu | Mu | Mu | Mu | Mu | Mu | Yuan |  |  |
|  | Fengxiang | Bolin | 9 | Hua luo | 6 | 5000 | 20000 | 25000 | 3 |  |  |  |  |  |  |  |  |  | Working outside |
|  |  |  | 9 | Caixia zhang | 7 | 4000 | 44000 | 48000 | 4 |  |  |  |  |  |  |  |  |  | Working outside |
|  |  |  | 9 | Fuhai ma | 2 |  | 13000 | 13000 | 2 |  |  |  |  |  |  |  |  |  | Working outside |
|  |  |  | 9 | Li an | 6 | 7000 | 28000 | 35000 | 6 |  |  |  |  |  |  |  |  |  | Working outside |
|  |  |  | 9 | Yanfang zhu | 1 | 2000 | 4000 | 6000 | 3 |  |  |  |  |  |  |  |  |  | (Child support) |
|  |  |  | 7 | Haiming an | 6 |  | 38000 | 38000 | 9.27 |  |  |  |  |  |  |  |  |  | Working outside |
|  |  |  | 7 | Yongliang an | 6 | 0 | 32000 | 32000 | 15.45 |  |  |  |  |  |  |  |  |  | Working outside |
|  |  |  | 7 | Hailou an | 3 |  | 32000 | 32000 | 12.27 |  |  |  |  |  |  |  |  |  | Business |
|  |  |  | 7 | Fu an | 6 | 10000 | 45000 | 55000 | 24.39 |  |  |  |  |  |  |  |  |  | Cultivation |
|  |  |  | 7 | Shuqin xie | 5 | 2000 | 60000 | 62000 | 13.41 |  |  |  |  |  |  |  |  |  | Working outside |
|  |  |  | 7 | Tianxin ren | 6 | 1000 | 22000 | 23000 | 18.17 |  |  |  |  |  |  |  |  |  | Working outside |
|  |  |  | 6 | Li li | 3 |  | 45000 | 45000 | 8 |  |  |  |  |  |  |  |  |  | Working outside |
|  |  |  | 6 | Qiang an | 6 |  | 35000 | 35000 | 13.3 |  |  |  |  |  |  |  |  |  | Restaurant |
|  |  |  | 6 | Dengshou an | 6 | 3000 | 59000 | 62000 | 15.24 |  |  |  |  |  |  |  |  |  | Business |
|  |  |  | 6 | Dengming an | 5 |  | 62000 | 62000 | 7.52 |  |  |  |  |  |  |  |  |  | Working outside |
|  |  |  | 3 | Junwen an | 6 | 3000 | 37000 | 40000 | 22.7 |  |  |  |  |  |  |  |  |  | Working outside |
|  |  |  | 8 | Yongming an | 6 |  | 35000 | 35000 | 10.8 |  |  |  |  |  |  |  |  |  | Working outside |
|  |  |  | 8 | Xiong yue | 4 |  | 38000 | 38000 | 7.28 |  |  |  |  |  |  |  |  |  | Working outside |
|  |  |  | 8 | Zuojie mou | 2 | 5000 | 20000 | 25000 | 19.9 |  |  |  |  |  |  |  |  |  | Agriculture |
|  |  |  | 8 | Suo an | 1 | 3000 | 39000 | 42000 | 8.5 |  |  |  |  |  |  |  |  |  | Agriculture |
|  |  | Subtotal |  |  | 93 | 45,000 | 708,000 | 753,000 | 224.2 |  |  |  |  |  |  |  |  |  |  |

Annex 2.2.2 Property of sample HHs of Dingxi City

| Serial | Town | Village | Group | Name | House | House area | Colored TV | Refrigerator | Wash machine | Tractor | Motorcycle | Pump | Big living stock | Internet | Telephone | Car | Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Rooms | M2 | Set | Set | Set | Set | Set | Set | Unit | Set | Set | Set |  |
|  | Fengxiang | Bolin | 9 | Hua luo | 4 | 120 | 1 |  | 1 |  | 1 |  |  | 1 | 2 | 1 |  |
|  |  |  | 9 | Caixia zhang | 8 | 300 | 2 | 1 | 1 |  | 1 |  |  | 1 | 2 | 2 |  |
|  |  |  | 9 | Fuhai ma | 2 | 60 | 1 |  | 1 |  | 1 |  |  |  | 1 | 1 |  |
|  |  |  | 9 | Li an | 6 | 300 | 1 |  | 1 |  | 1 |  |  | 1 | 2 | 1 |  |
|  |  |  | 9 | Yanfang zhu | 4 | 120 | 1 |  | 1 |  | 1 |  |  | 1 |  |  |  |
|  |  |  | 7 | Haiming an | 6 | 310 | 1 |  | 1 |  |  |  |  |  | 2 |  |  |
|  |  |  | 7 | Yongliang an | 6 | 310 | 1 |  | 1 |  |  |  |  |  | 2 |  |  |
|  |  |  | 7 | Hailou an | 4 | 150 | 1 |  | 1 |  |  |  |  |  | 1 |  |  |
|  |  |  | 7 | Fu an | 8 | 410 | 2 | 1 | 1 |  |  |  |  |  | 2 | 1 |  |
|  |  |  | 7 | Shuqin xie | 8 | 410 | 2 | 1 | 1 |  |  |  |  |  | 3 | 1 |  |
|  |  |  | 7 | Tianxin ren | 5 | 200 | 1 | 1 | 1 |  |  |  |  |  | 2 |  |  |
|  |  |  | 6 | Li li | 5 | 260 | 1 | 1 | 1 |  |  |  |  |  | 2 | 1 |  |
|  |  |  | 6 | Qiang an | 5 | 210 | 1 | 1 | 1 |  |  |  |  |  | 2 |  |  |
|  |  |  | 6 | Dengshou an | 5 | 260 | 2 | 1 | 1 |  |  |  |  |  | 3 | 1 |  |
|  |  |  | 6 | Dengming an | 5 | 260 | 2 | 1 | 1 |  |  |  |  |  | 2 | 1 |  |
|  |  |  | 3 | Junwen an | 5 | 310 | 2 | 1 | 1 |  |  |  |  |  | 2 | 1 |  |
|  |  |  | 8 | Yongming an | 5 | 310 | 2 | 1 | 1 |  |  |  |  |  | 2 |  |  |
|  |  |  | 8 | Xiong yue | 5 | 350 | 1 | 1 | 1 |  |  |  |  |  | 2 |  |  |
|  |  |  | 8 | Zuojie mou | 8 | 400 | 1 | 1 | 1 |  |  |  |  |  | 1 |  |  |
|  |  |  | 8 | Suo an | 5 | 450 | 1 | 1 | 1 |  |  |  |  |  | 1 |  |  |
|  |  |  | Subtotal |  | 109 | 5,500 | 27 | 13 | 20 | 0 | 5 | 0 | 0 | 4 | 36 | 11 | 0 |

Annex 2.2.3 Sampling of land compensation payment details for the first batch contract package

| Gourp | Name | Area |  | land price unit | amount | amount for trees | amount for ground attachments | Subtotal | Signature |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | M2 | Mu | Yuan / M2 | Yuan | Yuan | Yuan | Yuan |  |
| 9 | Wan Zhao | 191.27 | 0.287 | 75 | 14,345.25 |  |  | 14,345.25 |  |
| 9 | Wan Zhao | 1950 | 2.925 | 75 | 146,250 |  |  | 146,250 |  |
| 9 | Wan Zhao | 260 | 0.39 | 75 | 19,500 |  |  | 19,500 |  |
| 9 | Hulong An | 555.3 | 0.833 | 75 | 41,647.5 | 100 |  | 41,747.5 |  |
| 9 | Yunhua Zhu | 481.26 | 0.722 | 75 | 36,094.5 |  |  | 36,094.5 |  |
| 9 | Yunhua Zhu | 869.04 | 1.304 | 75 | 65,178 |  |  | 65,178 |  |
| 9 | Yunhua Zhu |  |  |  |  | 43,310 |  | 43,310 |  |
| 9 | Caixia Zhang | 1,100 | 1.65 | 75 | 82,500 |  |  | 82,500 |  |
| 9 | Caixia Zhang | 824.1 | 1.236 | 75 | 61,807.5 |  |  | 61,807.5 |  |
| 9 | Caixia Zhang | 840 | 1.26 | 75 | 63,000 |  |  | 63,000 |  |
| 9 | Caixia Zhang | 351.6 | 0.527 | 75 | 26,370 |  |  | 26,370 |  |
| 9 | Caixia Zhang |  |  |  |  | 9,888 |  | 9,888 |  |
| 9 | Yinglong An | 1,205.4 | 1.808 | 75 | 90,405 |  | 6,000 | 96,405 |  |
| 9 | Yichang Chen | 992.2 | 1.488 | 75 | 74,415 |  |  | 74,415 |  |
| 9 | Yichang Chen | 602 | 0.903 | 75 | 45,150 |  |  | 45,150 |  |

Annex 2.2.4 Sampling investigation on housing compensation

| AP | Village | Communtiy | No. | Construction structure | House usage | Construction area | Building evaluation | Attachments evaluation | Homestead compensation | Moving subsidy | Other expenses | New apartments | subtotal | Resettlement methods | New apartments | Set | New apartment unit location | Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | M2 | Yuan | Yuan | Yuan | Yuan | Yuan | Yuan | Yuan |  | M2 | set |  |  |
| Weiguo Yue | Bolin | Yuejiazhuang | 48 | Brick concret | Residential | 493.22 | 914186 | 126403 | 137340 | 2400 | 40800 |  | 1,221,129 | Relocation |  |  |  | 20160311 |
| Dong Ma | Bolin | 1 | 2 | Brick concret | Residential | 462.49 | 797732 | 47349 |  | 2400 | 185,441 |  | 1,032,922 | Monetary |  |  |  | 20160305 |
| Gui Yue | Bolin | Yuejiazhuang | 47 | Brick concret | Residential | 619.67 | 1109923.55 | 53354.77 | 51161 | 2400 | 43,806 |  | 1,260,645.32 | Relocation |  |  |  | 20160305 |
| Ximing Ma | Bolin | Majiazhuang | 3 | Brick concret | Residential | 349.82 | 541762 | 33340 |  |  |  | 399144 | 175,958 | Property swap | 295.97 | 3 | No.14,0704，No.14, 1701，No. 14, 0602 | 20160310 |
| Qiaolian Ma | Bolin | Majiazhuang | 6 | Brick concret | Non-residential | 41.4 | 18,812 | 42,990 |  | 2400 | 49,812 |  | 114,014 | Monetary |  |  |  | 20160310 |
| Hu Ma | Bolin | Majiazhuang | 3 | Brick concret | Non-residential | 376.73 | 596,217 | 52,000 | 72,389 | 2,400 | 102,389 |  | 753,006 | Relocation |  |  |  | 20160309 |

Annex 2.2.5 Sample survey of housing compensation（sample survey in October 2016）

| AP | Village | community | No. | Construction structure | House usage | Construction area | Construction evaluation | Attachments evaluation | Homestead compensation | Moving subsidy | Other costs | New appartments | Suttotal | Resettlement method |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | M2 | Yuan | Yuan | Yuan | Yuan | Yuan | Yuan | Yuan | 0 |
| Huan An | West ershipu | Baozi River | 21 | Brick-concrete, brick -wood | Residential | 707.38 | 1217980 | 71962 | 74498 | 2400 | 0 |  | 1396840 | Remote Relocation |
| Qiang An | Bolin | Qiangchang |  | Brick-concrete, brick -wood | Residential | 433.68 | 646353 | 214285 | 39960 | 2400 | 87780 |  | 950818 | Remote Relocation |
| Yingwen An | Bolin | Beizhuang | 4 | Brick-concrete, earth-wood | Residential | 150.44 | 146647 | 23543 | 8280 | 2400 | 38280 |  | 210870 | Remote Relocation |
| Xinwen an | Bolin | Beizhuang | 3 | Brick-concrete | Residential | 614.52 | 1132056 | 92952 | 36360 | 2400 | 66360 |  | 1200816 | Remote Relocation |
| Yuan an | West ershipu | Baozi River | 22 | Brick-concrete, earth-wood | Residential | 901.19 | 1600909 | 41170 |  |  |  |  | 1928779 | monetary compensation |
| Xixian jing | West ershipu | Baozi River | 37 | Brick-concrete, earth-wood | Residential | 606.15 | 1213924 | 1281260 |  |  |  |  | 1567306 | monetary compensation |
| Zhigang an | Bolin | Beizhuang | 14 | Brick-concrete | Residential | 196.82 | 310096 |  | 2160 |  |  |  | 360239 | Remote Relocation |
| Bi shu | Bolin | Beizhuang | 11 | Brick-concrete, brick -wood | Residential | 384.07 | 700007 | 48753 | 38340 | 2400 | 70740 |  | 819500 | Remote Relocation |
| Zhengwen an | Bolin | Beizhuang | 2 | Brick-concrete, earth-wood | Residential | 572.4 | 935946 | 22163 |  |  |  |  | 1171539 | monetary compensation |
| Qi an | Bolin | Beizhuang | 2 | Brick-concrete | Residential | 512.72 | 866968 | 5756 |  |  |  |  | 1044371 | monetary compensation |
| Zhengping zhu | Bolin | Beizhuang | 10 | Earth-wood | Residential | 72 | 74908.8 | 10245 | 11160 | 2400 | 71100 |  | 199814 | monetary compensation |
| Jun chen | West ershipu | Baozi River | 29 | Brick-concrete | Residential | 354 | 660266 | 54161 |  |  |  |  |  | Property swap |
| Junming ma | Bolin | 二 |  | Brick-concrete | Residential | 1115.79 | 2080948 | 45232 |  |  | 225342 |  | 2513362 | monetary compensation |
| Peng an | Bolin | Beizhuang | 17 | Brick-concrete, earth-wood | Residential | 659.5 | 1062237 | 44476 |  |  | 315961 |  | 1425074 | monetary compensation |
| Peng yue | Bolin | Beizhuang | 1 | Brick-concrete, brick -wood | Residential | 618.74 | 1038426 | 39868 |  |  | 45750 |  | 1156444 | Remote Relocation |

Annex 2.2.6 Sampling survey on housing compensation (April 2017 sampling)

| Village | community | Number | Construction structure | Housing usage | Construction area | Building Assessment | Attachments assessment | Homestead compensation | Relocation subsidy | Other fees | New houses | Subtotal | Resettlement method |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | M2 | yuan | yuan | yuan | yuan | yuan | yuan | yuan |  |
| Bolin | Yuejiazhuang Group | 5 | Brick wood | residential | 138.58 | 170779 | 31386 | 96666 | 2400 | 30000 |  | 244231 | Offsite relocation |
| Bolin | Yuejiazhuang Group | 5 | Brick concrete | residential | 696.94 | 1286569 | 5230 |  | 2400 |  |  | 1504067 | Momentary |
| North Ershilipu | Nanzhuang | 17 | Brick wood | residential | 24.96 | 19274 | 0 |  | 2400 | 31927 |  | 53601 | Momentary |
| Bolin | Beizhuang | 17 | Brick concrete | residential | 640.16 | 1079336 | 144201 |  | 2400 | 122354 |  | 1378292 | Momentary |
| West Ershilipu | Baozihe Group |  | Brick concrete | residential | 88.23 | 134217 | 200 |  |  |  |  |  | Property rights |
| Bolin | Beizhuang | 15 | Brick concrete | residential | 192.12 | 443370 | 106603 | 20160 | 2400 | 30000 |  | 495930 | Offsite relocation |

Note: the serial number here is from the memorandum, the same below.

The actual number of HHs is larger than planned, because there are some families splitted into more HHs in the later stage.